## Dashboard
GradNavi Sprint 3 Integration & Testing Dashboard
Sprint 3: Application Documents and Interview Preparation ¦ 7 Sep to 18 Sep 2026 ¦ Formally closed 9 Oct 2026
Plan Item | Current Value |  | Status | Count | Metric | Value
Integration Branch | feature/sprint-3 |  | Pass | 100 | Executed/Ready | 100
Evidence Folder | docs/testing/evidence/sprint-3/ |  | Fail | 0 | Blocked % | 0%
Total Test Cases | 100 |  | Blocked | 0
Pass | 100 |  | Not Run | 0
Fail | 0 |  | Retest | 0
Blocked | 0
Current Integration Gate
Gate | Owner | Current State | Entry Requirement | Dependency / Note
WBS 6.2 AI prompt templates & safety | Jerald | Merged / verified | Required | Complete
WBS 6.3 Resume generation backend | MD | Merged / verified | Required | Resume backend tests pass on current shared backend baseline
WBS 6.4 Cover letter generation backend | MD | Merged / verified | Required | 48/48 documents tests passed; merged into feature/sprint-3
WBS 6.5 Resume and cover letter interface | Joyee | Merged / verified | Required | Completed through PR #59; successor integration verified in PR #78
WBS 6.6 Interview question and feedback API | Jerald | Merged / verified | Required | 38/38 focused tests passed; merged into feature/sprint-3
WBS 6.7 Interview preparation interface | Joyee | Verified / successor integrated | Required | PR #63 contribution superseded; final implementation integrated and verified through PR #78
WBS 6.8 / 6.9 Entry Rule
Rule | Status | Meaning
6.8 integration | Pass | Formal closeout accepts complete Sprint 3 integration using verified successor baseline evidence from PR #78 and final WBS 7.9.
6.9 Sprint 3 testing | Pass | 100/100 Sprint 3 test cases are Pass after formal evidence reconciliation.
Blocked != Fail | Closed | No blocked Sprint 3 cases remain after formal closeout.
Evidence | Captured | Evidence Index and closeout traceability are updated for all Sprint 3 cases.

## Test Cases
GradNavi Sprint 3 Test Case Tracker
WBS 6.2 to 6.9 ¦ Application Documents and Interview Preparation ¦ Evidence: docs/testing/evidence/sprint-3/
Status rule: Blocked means a required dependency is unavailable. Blocked is not Fail. Component-level Pass does not imply WBS 6.8 integration has passed.
Test ID | WBS | Area | Requirement | Priority | Test Level | Test Case | Preconditions | Steps | Expected Result | Owner | Status | Blocked By | Actual Result | Evidence ID | Defect Ref | Automation | Notes
S3-TC-001 | 6.8/6.9 | Baseline | NFR-07,NFR-12 | Critical | Baseline | Confirm feature/sprint-3 is current and clean | All required Sprint 3 PRs intended for integration are merged. | Fetch remote; checkout feature/sprint-3; pull; run git status. | Branch is current, clean, and contains expected Sprint 3 merges. | All Members | Pass |  | PASS at formal closeout. WBS 6.5 was merged to feature/sprint-3 through PR #59. The final WBS 6.7 implementation was later superseded and integrated on the successor feature/sprint-4 baseline through PR #78. Final WBS 7.9 integration and testing completed 129/129 planned Sprint 4 cases as Pass. Sprint 3 closeout accepts the verified successor integration baseline. | S3-EV-007 |  | Manual | Formal closeout traceability note: the historical feature/sprint-3 branch did not receive the final WBS 6.7 merge. The accepted final implementation is traced through PR #78 and final WBS 7.9 verification.
S3-TC-002 | 6.8/6.9 | Baseline | NFR-12 | Critical | Baseline | Run Django system check on integrated branch | Backend environment active; PostgreSQL available if settings require it. | Run python manage.py check. | System check identifies no issues. | All Members | Pass |  | Django system check passed on current feature/sprint-3 backend baseline with no issues. | S3-EV-009 |  | Automated | Interim backend baseline pass. Rerun after WBS 6.5 and 6.7 merge before final Sprint 3 exit.
S3-TC-003 | 6.8/6.9 | Baseline | NFR-12,NFR-15 | Critical | Database | Confirm migration consistency | Integrated branch current; PostgreSQL running. | Run showmigrations and makemigrations --check; apply migrations in disposable/local environment if required. | No unintended migration drift; required migrations apply successfully. | MD | Pass |  | makemigrations --check reported no changes. Test database migrations applied successfully during the 410-test regression run. | S3-EV-009 |  | Hybrid | Interim backend baseline pass. Final migration review remains part of WBS 6.9 after WBS 6.8.
S3-TC-004 | 6.8/6.9 | Baseline | NFR-07,NFR-12 | High | Frontend | Run frontend lint | Frontend dependencies installed. | Run npm lint command defined by project. | Lint completes without blocking errors. | Joyee | Pass |  | PASS at formal closeout. Frontend lint completed with 0 warnings and 0 errors during WBS 6.5 verification in PR #59 and again during the later integrated Student workflow verification in PR #78. | S3-EV-005 |  | Automated | Accepted from verified implementation and successor integration evidence.
S3-TC-005 | 6.8/6.9 | Baseline | NFR-07,NFR-11,NFR-12 | Critical | Frontend | Run production frontend build | Frontend dependencies installed and environment configured. | Run npm build command defined by project. | Production build completes successfully. | Joyee | Pass |  | PASS at formal closeout. The Vite production build completed successfully during WBS 6.5 verification in PR #59 and again during the later integrated Student workflow verification in PR #78. | S3-EV-005 |  | Automated | Accepted from verified implementation and successor integration evidence.
S3-TC-006 | 6.2 | AI Contracts & Safety | FR-08,FR-09,FR-10,FR-16,NFR-14 | Critical | Unit | Approved AI operations are defined | WBS 6.2 merged. | Run ai_services prompt/schema tests. | Resume, cover letter, interview questions, and interview feedback operations use approved identifiers. | Jerald | Pass |  | Verified by WBS 6.2 automated tests. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-007 | 6.2 | AI Contracts & Safety | FR-08,NFR-06,NFR-14 | Critical | Security | Resume profile privacy allowlist excludes private fields | WBS 6.2 merged. | Run privacy tests against Student Profile mapping. | Only approved profile context reaches AI prompt preparation. | Jerald | Pass |  | Privacy allowlist tests passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-008 | 6.2 | AI Contracts & Safety | FR-08,FR-09,FR-10,NFR-14 | Critical | Security | User-controlled descriptions remain untrusted | WBS 6.2 merged. | Run prompt trust-boundary tests. | User-controlled text stays in untrusted content and never becomes system instructions. | Jerald | Pass |  | Trust separation tests passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-009 | 6.2 | AI Contracts & Safety | FR-08,NFR-14 | High | Unit | Resume output requires draft and review flags | WBS 6.2 merged. | Validate ResumeDraft schema. | is_draft and requires_user_review must remain true. | Jerald | Pass |  | Schema tests passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-010 | 6.2 | AI Contracts & Safety | FR-09,NFR-14 | High | Unit | Cover letter output requires draft and review flags | WBS 6.2 merged. | Validate CoverLetterDraft schema. | Generated cover letter remains reviewable draft content. | Jerald | Pass |  | Schema tests passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-011 | 6.2 | AI Contracts & Safety | FR-10,NFR-14 | Critical | Unit | Interview output excludes hiring probability | WBS 6.2 merged. | Validate InterviewQuestionSet and InterviewFeedback schemas. | Hiring probability fields are rejected. | Jerald | Pass |  | Safety schema tests passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-012 | 6.2 | AI Contracts & Safety | FR-10,NFR-14 | Critical | Unit | Interview output excludes pass/fail classification | WBS 6.2 merged. | Validate interview output schemas. | Pass/fail hiring decisions are not accepted output fields. | Jerald | Pass |  | Safety schema tests passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-013 | 6.2 | AI Contracts & Safety | FR-08,FR-09,FR-10,NFR-13 | High | Architecture | AIProvider contract stays provider-independent | WBS 6.2 merged. | Inspect provider base contract and service-facing interfaces. | Sprint 3 code depends on shared provider contract, not provider SDK code. | Jerald | Pass |  | Provider contract present and reused. | S3-EV-001A; S3-EV-001B |  | Manual
S3-TC-014 | 6.2 | AI Contracts & Safety | FR-18,NFR-13 | High | Unit | Shared AI exception hierarchy is available | WBS 6.2 merged. | Run exception import/behaviour tests. | Input, privacy, safety, provider, timeout, validation, and unsupported-operation errors are distinct. | Jerald | Pass |  | Exception hierarchy verified. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-015 | 6.2 | AI Contracts & Safety | FR-08,FR-09,FR-10,NFR-12 | High | Regression | Focused AI service tests pass | WBS 6.2 branch evidence available. | Run focused ai_services tests. | Focused WBS 6.2 suite passes. | Jerald | Pass |  | Focused WBS 6.2 suite passed. | S3-EV-001A; S3-EV-001B |  | Automated
S3-TC-016 | 6.2 | AI Contracts & Safety | NFR-12 | Critical | Regression | Backend regression remains green after WBS 6.2 | WBS 6.2 branch evidence available. | Run full backend suite. | All backend tests pass after WBS 6.2 changes. | Jerald | Pass |  | Full backend regression passed at WBS 6.2 checkpoint. | S3-EV-001C; S3-EV-001D |  | Automated
S3-TC-017 | 6.2 | AI Contracts & Safety | NFR-07,NFR-12 | High | Baseline | WBS 6.2 branch is clean and documented | WBS 6.2 closeout evidence available. | Review branch status, commit history, and closeout record. | Working tree is clean and implementation commits are traceable. | Jerald | Pass |  | Branch status and commits captured. | S3-EV-001E |  | Manual
S3-TC-018 | 6.3 | Resume Backend | FR-08 | Critical | API | Resume endpoint requires JWT | WBS 6.3 merged into feature/sprint-3. | POST resume endpoint without token. | 401 controlled error. | MD | Pass |  | Authentication-required resume API test passed in the shared 410-test backend regression. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-019 | 6.3 | Resume Backend | FR-08,NFR-06 | Critical | Security | Resume endpoint rejects client profile identifiers | WBS 6.3 merged into feature/sprint-3. | Send student_profile_id, user_id, email, prompt, or skills. | 400 validation error and no client ownership override. | MD | Pass |  | Unexpected client ownership/profile/prompt fields were rejected by automated resume API tests. | S3-EV-009A |  | Hybrid | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-020 | 6.3 | Resume Backend | FR-08,NFR-06 | Critical | Integration | Authenticated Student profile supplies resume context | WBS 6.3 merged into feature/sprint-3. | Call resume endpoint for Student A while Student B exists. | Provider prompt contains only Student A approved profile facts. | MD | Pass |  | Authenticated Student profile isolation and approved profile-context tests passed. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-021 | 6.3 | Resume Backend | FR-08 | High | Integration | Resume generation reuses WBS 6.2 prompt builder | WBS 6.3 merged into feature/sprint-3. | Invoke resume service with fake provider. | Provider receives RESUME_GENERATION prompt package. | MD | Pass |  | Resume service used the approved RESUME_GENERATION provider/output contract in automated tests. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-022 | 6.3 | Resume Backend | FR-08,FR-16 | Critical | API | Resume response is structured editable draft | WBS 6.3 merged into feature/sprint-3. | Use fake provider returning ResumeDraft. | 200 response contains draft fields and review flags. | MD | Pass |  | Structured ResumeDraft response and required review flags passed automated API tests. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-023 | 6.3 | Resume Backend | FR-18 | High | API | Unconfigured provider fails closed | WBS 6.3 merged into feature/sprint-3. | Call endpoint with default provider seam. | 503 external_service_unavailable. | MD | Pass |  | Default resume provider seam failed closed with controlled 503 behaviour in automated tests. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-024 | 6.3 | Resume Backend | FR-18 | High | API | Provider timeout is controlled | WBS 6.3 merged into feature/sprint-3. | Inject provider timeout. | 503 controlled error without stack trace. | MD | Pass |  | AIProviderTimeoutError propagation and controlled shared AI service failure handling passed automated documents tests. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-025 | 6.3 | Resume Backend | NFR-14 | High | Security | Private profile fields stay outside provider prompt | WBS 6.3 merged into feature/sprint-3. | Populate private user/profile fields; generate draft. | Email, private interests, personality responses, URLs, and internal metadata are absent. | MD | Pass |  | Private profile fields were excluded from the resume provider prompt in automated privacy tests. | S3-EV-009A |  | Hybrid | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-026 | 6.3 | Resume Backend | NFR-12 | High | Regression | WBS 6.3 focused backend suite passes | WBS 6.3 merged into feature/sprint-3. | Run documents resume tests. | All WBS 6.3 focused tests pass. | MD | Pass |  | All resume-generation automated tests included in the current shared backend regression passed. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-027 | 6.3 | Resume Backend | NFR-12 | Critical | Regression | Backend regression remains green after WBS 6.3 | WBS 6.3 merged into feature/sprint-3. | Run full backend suite on feature/sprint-3. | All backend tests pass. | MD | Pass |  | Current feature/sprint-3 full backend regression passed 410/410 tests. | S3-EV-009A |  | Automated | Verified on the current merged feature/sprint-3 backend baseline. Dedicated WBS 6.3 evidence remains useful for team closeout.
S3-TC-028 | 6.4 | Cover Letter Backend | FR-09,NFR-05 | Critical | API | Cover letter endpoint requires JWT | WBS 6.4 merged and available on feature/sprint-3. | Call endpoint without token. | 401 controlled error. | MD | Pass |  | Cover-letter authentication-required test passed. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-029 | 6.4 | Cover Letter Backend | FR-09 | Critical | API | Cover letter request accepts one target job description | WBS 6.4 merged and available on feature/sprint-3. | Submit approved job-description payload. | Request validates and proceeds to service. | MD | Pass |  | Validated job-description request contract passed automated tests. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-030 | 6.4 | Cover Letter Backend | FR-09 | High | API | Cover letter rejects blank job description | WBS 6.4 merged and available on feature/sprint-3. | Submit blank/whitespace job description. | 400 validation error. | MD | Pass |  | Blank job description was rejected by API and input-contract tests. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-031 | 6.4 | Cover Letter Backend | FR-09,NFR-06 | Critical | Security | Cover letter rejects client profile identifiers and prompt overrides | WBS 6.4 merged and available on feature/sprint-3. | Submit user_id, student_profile_id, prompt or unsupported fields. | 400 and no ownership override. | MD | Pass |  | Client ownership identifiers, prompt overrides, and unexpected fields were rejected. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-032 | 6.4 | Cover Letter Backend | FR-09,NFR-06 | Critical | Integration | Authenticated Student profile supplies cover letter facts | WBS 6.4 merged and available on feature/sprint-3. | Generate for Student A while Student B exists. | Only Student A approved profile facts reach prompt context. | MD | Pass |  | Authenticated Student profile supplied approved cover-letter context and cross-user selection was blocked. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-033 | 6.4 | Cover Letter Backend | FR-09,NFR-14 | Critical | Security | Job description remains untrusted content | WBS 6.4 merged and available on feature/sprint-3. | Submit malicious/instruction-like job description. | Job description stays in untrusted content. | MD | Pass |  | Job description remained untrusted content and instruction-like text did not become trusted instructions. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-034 | 6.4 | Cover Letter Backend | FR-09,FR-16,NFR-14 | Critical | Integration | Cover letter output is tailored but does not invent facts | WBS 6.4 merged and available on feature/sprint-3. | Use controlled fake provider/output validation. | Structured draft references supplied role context without fabricated Student claims. | MD | Pass |  | CoverLetterDraft contract, privacy mapping, supplied-fact boundaries, and structured output validation passed. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-035 | 6.4 | Cover Letter Backend | FR-09,FR-16 | High | API | Generated cover letter requires user review | WBS 6.4 merged and available on feature/sprint-3. | Inspect response flags. | Draft/review flags remain enforced. | MD | Pass |  | Generated cover-letter draft retained draft/requires_user_review flags. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-036 | 6.4 | Cover Letter Backend | FR-18 | High | API | Provider unavailable/timeout returns controlled error | WBS 6.4 merged and available on feature/sprint-3. | Exercise provider error paths. | Controlled service error, no sensitive internals. | MD | Pass |  | Default provider seam and shared AI service failure paths returned controlled service errors. | S3-EV-004A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-037 | 6.4 | Cover Letter Backend | NFR-12 | Critical | Regression | WBS 6.4 focused tests and backend regression pass | WBS 6.4 merged and available on feature/sprint-3. | Run focused and full backend suites. | All tests pass. | MD | Pass |  | 48/48 documents tests passed on the merged Sprint 3 baseline; current shared feature/sprint-3 backend regression passed 410/410. | S3-EV-004A; S3-EV-009A |  | Hybrid | WBS 6.4 is merged into feature/sprint-3 and verified against the updated Sprint 3 backend baseline.
S3-TC-038 | 6.5 | Document Interface | FR-08,NFR-05 | Critical | UI | Resume builder page loads for authenticated Student | WBS 6.5 available and backend endpoints integrated. | Open Resume Builder after login. | Page loads and protected route behaviour is correct. | Joyee | Pass |  | PASS at formal closeout. Resume Builder loaded successfully for an authenticated Student during WBS 6.5 manual UI verification and later integrated workflow verification. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-039 | 6.5 | Document Interface | FR-08 | Critical | Integration | Resume builder invokes backend resume endpoint | WBS 6.5 available and backend endpoints integrated. | Generate resume from UI. | Frontend calls approved resume API and renders response. | Joyee | Pass |  | PASS at formal closeout. Resume generation from the frontend to the approved backend flow was verified during WBS 6.5 and later integrated Student workflow verification. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-040 | 6.5 | Document Interface | FR-08,FR-16 | Critical | UI | Resume draft is editable before save/export | WBS 6.5 available and backend endpoints integrated. | Edit generated resume content. | Student edits generated content before any save/export action. | Joyee | Pass |  | PASS at formal closeout. Editable Resume draft behaviour and document actions were verified during WBS 6.5 interface verification and later integrated workflow verification. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-041 | 6.5 | Document Interface | FR-18,NFR-01 | High | UI | Resume loading and provider-unavailable states are clear | WBS 6.5 available and backend endpoints integrated. | Trigger loading and 503 paths. | UI shows useful loading/error state without technical leakage. | Joyee | Pass |  | PASS at formal closeout. Resume loading and controlled provider-error behaviour are accepted from the verified WBS 6.5 provider seam and later Sprint 4 controlled AI-error integration coverage. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-042 | 6.5 | Document Interface | FR-09 | Critical | UI | Cover letter requires specific job description input | WBS 6.5 available and backend endpoints integrated. | Open Cover Letter Builder and attempt generation without job description. | UI requires or clearly validates job description. | Joyee | Pass |  | PASS at formal closeout. Cover Letter required-field behaviour, including required job information and disabled generation state, was verified in WBS 6.5. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-043 | 6.5 | Document Interface | FR-09 | Critical | Integration | Cover letter builder invokes backend cover-letter endpoint | WBS 6.5 available and backend endpoints integrated. | Submit role/job context and generate. | Frontend calls approved API and renders draft. | Joyee | Pass |  | PASS at formal closeout. Cover Letter generation from the frontend to the approved backend flow was verified during WBS 6.5 and later integrated Student workflow verification. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-044 | 6.5 | Document Interface | FR-09,FR-16 | Critical | UI | Cover letter draft is editable before save/export | WBS 6.5 available and backend endpoints integrated. | Edit generated cover-letter content. | Student edits generated text before save/export. | Joyee | Pass |  | PASS at formal closeout. Editable Cover Letter draft behaviour and document actions were verified during WBS 6.5 and later integrated workflow verification. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-045 | 6.5 | Document Interface | FR-16,NFR-14 | High | UI | Resume and cover-letter pages show AI limitations/review state | WBS 6.5 available and backend endpoints integrated. | Inspect generated-content presentation. | User is informed content is AI-generated/draft and requires review. | Joyee | Pass |  | PASS at formal closeout. Resume and Cover Letter generated-content review and limitation states were verified in WBS 6.5 and preserved in later integration. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-046 | 6.5 | Document Interface | NFR-02 | High | UI | Document UI works at desktop, tablet, and mobile widths | WBS 6.5 available and backend endpoints integrated. | Test common responsive widths. | Core controls and generated content remain usable. | Joyee | Pass |  | PASS at formal closeout. Document workflows were verified across desktop, tablet, and mobile layouts during the later integrated Student workflow verification. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-047 | 6.5 | Document Interface | NFR-10,NFR-11 | High | UI | Document UI supports labels, keyboard use, and useful validation | WBS 6.5 available and backend endpoints integrated. | Run accessibility/browser checks in Chrome, Edge, Firefox. | Core document flow is usable and compatible. | Joyee | Pass |  | PASS at formal closeout. Document form controls, HelpTip keyboard interaction, validation behaviour, and final compatibility coverage are accepted from WBS 6.5 and final Sprint 4 integration testing. | S3-EV-005 |  | Manual | Accepted from PR #59 WBS 6.5 verification and, where required, PR #78 / final WBS 7.9 successor integration evidence.
S3-TC-048 | 6.6 | Interview API | FR-10,NFR-05 | Critical | API | Interview question endpoint requires JWT | WBS 6.6 merged into feature/sprint-3. | POST questions endpoint without token. | 401 controlled error. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-049 | 6.6 | Interview API | FR-10,NFR-05 | Critical | API | Interview feedback endpoint requires JWT | WBS 6.6 merged into feature/sprint-3. | POST feedback endpoint without token. | 401 controlled error. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-050 | 6.6 | Interview API | FR-10,NFR-05 | Critical | API | Invalid JWT is rejected by both interview endpoints | WBS 6.6 merged into feature/sprint-3. | Use invalid bearer token. | 401 token_not_valid controlled response. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-051 | 6.6 | Interview API | FR-10 | High | Unit | Interview question request applies default count 5 | WBS 6.6 merged into feature/sprint-3. | Validate request without question_count. | Validated question_count equals 5. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-052 | 6.6 | Interview API | FR-10 | High | Unit | Interview question count enforces 1 to 10 | WBS 6.6 merged into feature/sprint-3. | Validate 0 and 11 counts. | Out-of-range values are rejected. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-053 | 6.6 | Interview API | FR-10 | High | Unit | Interview question count rejects string coercion | WBS 6.6 merged into feature/sprint-3. | Submit question_count as string '5'. | Request is rejected as invalid integer. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-054 | 6.6 | Interview API | FR-10,NFR-06,NFR-14 | Critical | Security | Interview endpoints reject unexpected ownership/prompt fields | WBS 6.6 merged into feature/sprint-3. | Submit user_id, student_profile_id, or prompt fields. | 400 validation error. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Hybrid | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-055 | 6.6 | Interview API | FR-10,NFR-14 | Critical | Security | Target role and job description remain untrusted | WBS 6.6 merged into feature/sprint-3. | Generate questions with role/job text. | User text appears only in untrusted content. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Hybrid | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-056 | 6.6 | Interview API | FR-10,NFR-13 | High | Integration | Question generation uses approved WBS 6.2 operation/output contract | WBS 6.6 merged into feature/sprint-3. | Invoke service with fake provider. | Provider receives INTERVIEW_QUESTION_GENERATION and InterviewQuestionSet. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-057 | 6.6 | Interview API | FR-10,NFR-14 | Critical | Security | Interview feedback text remains untrusted | WBS 6.6 merged into feature/sprint-3. | Generate feedback with role/question/answer. | All supplied text stays in untrusted content. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Hybrid | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-058 | 6.6 | Interview API | FR-10,NFR-13 | High | Integration | Feedback generation uses approved operation/output contract | WBS 6.6 merged into feature/sprint-3. | Invoke service with fake provider. | Provider receives INTERVIEW_FEEDBACK and InterviewFeedback. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-059 | 6.6 | Interview API | FR-10,NFR-14 | Critical | Security | Interview responses exclude hiring probability and pass/fail | WBS 6.6 merged into feature/sprint-3. | Inspect structured API responses. | No hiring_probability or pass_fail fields. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Hybrid | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-060 | 6.6 | Interview API | FR-18 | High | API | Provider unavailable or timeout returns controlled 503 | WBS 6.6 merged into feature/sprint-3. | Exercise default seam and timeout provider. | 503 external_service_unavailable. | Jerald | Pass |  | Verified by WBS 6.6 automated tests. | S3-EV-002F |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-061 | 6.6 | Interview API | NFR-12 | Critical | Regression | Focused WBS 6.6 tests and full backend regression pass | WBS 6.6 merged into feature/sprint-3. | Run interviews suite, then full backend suite. | 38/38 focused interview tests pass and the current full backend regression remains green. | Jerald | Pass |  | 38/38 interview tests passed post-merge; current shared feature/sprint-3 full backend regression passed 410/410. | S3-EV-002F; S3-EV-009A; S3-EV-009B |  | Automated | Component-level result verified after merge. WBS 6.8 end-to-end integration remains blocked until WBS 6.5 and 6.7 are ready.
S3-TC-062 | 6.7 | Interview Interface | FR-10,NFR-05 | Critical | UI | Interview preparation page loads for authenticated Student | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Open interview preparation after login. | Protected page loads. | Joyee | Pass |  | PASS at formal closeout. The protected Interview Preparation page was verified in the final integrated Student workflow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-063 | 6.7 | Interview Interface | FR-10 | Critical | Integration | Question generation UI sends target role and optional job description | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Generate interview questions from UI. | Request matches API contract. | Joyee | Pass |  | PASS at formal closeout. Interview question generation from the UI with target career context was verified in the final integrated workflow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-064 | 6.7 | Interview Interface | FR-10 | High | UI | Generated questions render in backend order | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Generate multiple questions. | Questions and focus areas render correctly. | Joyee | Pass |  | PASS at formal closeout. Generated interview questions and focus areas rendered through the integrated Interview Preparation flow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-065 | 6.7 | Interview Interface | FR-10 | Critical | UI | Student can type an answer for a selected question | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Select question and type answer. | Answer input is available and retains typed text during flow. | Joyee | Pass |  | PASS at formal closeout. The Student answer input retained typed answer content during the interview practice flow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-066 | 6.7 | Interview Interface | FR-10 | Critical | Integration | Feedback UI calls feedback endpoint with selected question and answer | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Submit typed answer. | Approved feedback API is called. | Joyee | Pass |  | PASS at formal closeout. The integrated Interview Preparation flow submitted the selected question and typed answer for feedback. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-067 | 6.7 | Interview Interface | FR-10,NFR-01 | High | UI | Feedback strengths and improvements render clearly | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Receive structured feedback. | Strengths, improvements, summary, and suggested response display. | Joyee | Pass |  | PASS at formal closeout. Structured interview feedback rendered successfully in the final integrated flow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-068 | 6.7 | Interview Interface | FR-16,NFR-14 | High | UI | Interview UI shows AI limitation/review state | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Inspect generated questions and feedback. | AI-generated/review-required state is visible. | Joyee | Pass |  | PASS at formal closeout. Interview AI review and limitation messaging was preserved in the integrated flow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-069 | 6.7 | Interview Interface | FR-18,NFR-01 | High | UI | Interview UI handles loading, validation, and provider errors | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Trigger blank answer, loading, and 503. | Controlled useful UI states appear. | Joyee | Pass |  | PASS at formal closeout. Interview loading, validation, controlled provider-error, retry, and feedback states were verified across the later integrated implementation and Interview AI remediation. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-070 | 6.7 | Interview Interface | NFR-02 | High | UI | Interview UI works responsively | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Test desktop/tablet/mobile widths. | Core controls remain usable. | Joyee | Pass |  | PASS at formal closeout. Interview Preparation was verified across desktop, tablet, and mobile layouts in the later integrated workflow. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-071 | 6.7 | Interview Interface | NFR-10,NFR-11 | High | UI | Interview UI supports keyboard and current browsers | WBS 6.7 available; WBS 6.5 predecessor complete; WBS 6.6 API merged. | Test keyboard, Chrome, Edge, Firefox. | Core flow remains usable and compatible. | Joyee | Pass |  | PASS at formal closeout. Interview keyboard and current-browser compatibility are accepted from the final Sprint 4 WBS 7.9 compatibility closeout. | S3-EV-006 |  | Manual | PR #63 is retained as the original WBS 6.7 contribution record. Its final implementation was superseded and integrated through PR #78, with Interview AI verification also recorded in PR #74.
S3-TC-072 | 6.8 | Document & Interview Integration | NFR-07,NFR-12 | Critical | Baseline | Integrated branch contains WBS 6.3 to 6.7 deliverables | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Review feature/sprint-3 history and paths. | All required predecessor work is present. | All Members | Pass |  | PASS at formal closeout. WBS 6.3, 6.4, 6.5, and 6.6 were present in the Sprint 3 history. The final WBS 6.7 implementation was later superseded and integrated through PR #78 on feature/sprint-4. Formal Sprint 3 closeout accepts that verified successor integration evidence. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-073 | 6.8 | Document & Interview Integration | FR-08,FR-16 | Critical | E2E | Resume UI to API flow works end to end | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Login; open Resume Builder; generate; review/edit. | Resume draft returns and is editable. | All Members | Pass |  | PASS at formal closeout. Resume UI to API generation and review flow was verified in the later integrated Student workflow and final Sprint 4 end-to-end smoke. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-074 | 6.8 | Document & Interview Integration | FR-09,FR-16 | Critical | E2E | Cover letter UI to API flow works end to end | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Login; provide one job description; generate; review/edit. | Tailored cover-letter draft returns and is editable. | All Members | Pass |  | PASS at formal closeout. Cover Letter UI to API generation and review flow was verified in the later integrated Student workflow and final Sprint 4 end-to-end smoke. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-075 | 6.8 | Document & Interview Integration | FR-10 | Critical | E2E | Interview question UI to API flow works end to end | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Login; open interview prep; generate questions. | Question set returns and renders. | All Members | Pass |  | PASS at formal closeout. Interview question UI to API flow was verified in PR #78 and final Sprint 4 Interview regression. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-076 | 6.8 | Document & Interview Integration | FR-10 | Critical | E2E | Interview feedback UI to API flow works end to end | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Answer generated question and request feedback. | Structured feedback returns and renders. | All Members | Pass |  | PASS at formal closeout. Interview feedback UI to API flow was verified in PR #78, PR #74, and final Sprint 4 Interview regression. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-077 | 6.8 | Document & Interview Integration | NFR-05,NFR-06 | Critical | Security | Document and interview flows preserve authenticated Student context | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Run flows with Student A and Student B. | No cross-student protected profile data appears. | All Members | Pass |  | PASS at formal closeout. Student-context privacy and ownership controls are accepted from the integrated Student workflow privacy verification and final Sprint 4 security/privacy regression coverage. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-078 | 6.8 | Document & Interview Integration | FR-08,NFR-06,NFR-14 | Critical | Security | Resume flow rejects client profile/prompt manipulation | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Attempt UI/API manipulation with ownership/prompt fields. | Request is rejected; service not invoked with attacker-supplied ownership. | All Members | Pass |  | PASS at formal closeout. Resume ownership and prompt-manipulation protections are accepted from Sprint 3 backend safety tests plus final successor security and integration verification. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-079 | 6.8 | Document & Interview Integration | FR-09,NFR-14 | Critical | Security | Cover letter flow rejects prompt injection as instruction | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Use instruction-like text inside job description. | Text stays untrusted and cannot override system rules. | All Members | Pass |  | PASS at formal closeout. Cover Letter job-description trust boundaries and prompt-injection protections are accepted from Sprint 3 safety tests plus later integrated validation. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-080 | 6.8 | Document & Interview Integration | FR-10,NFR-14 | Critical | Security | Interview flow rejects prompt injection as instruction | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Use instruction-like role/job/answer text. | Text stays untrusted and safety contract holds. | All Members | Pass |  | PASS at formal closeout. Interview untrusted-input and safety-contract behaviour is accepted from Sprint 3 API safety tests and later Interview AI validation. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-081 | 6.8 | Document & Interview Integration | FR-16,NFR-14 | High | Integration | Generated content consistently shows review-required state | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Generate resume, cover letter, interview content. | All AI outputs communicate limitations/review requirement. | All Members | Pass |  | PASS at formal closeout. Review-required and AI limitation states are accepted from the verified Resume, Cover Letter, and Interview integrated workflows. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-082 | 6.8 | Document & Interview Integration | FR-18 | High | Integration | Provider unavailable state is consistent across Sprint 3 features | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Trigger default/unavailable provider across features. | Controlled error response and useful frontend state. | All Members | Pass |  | PASS at formal closeout. Controlled provider-unavailable and validation-error handling was verified across the document and Interview service boundaries and later Sprint 4 AI integration. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-083 | 6.8 | Document & Interview Integration | NFR-05 | Critical | Integration | Invalid/expired authentication is handled consistently | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Run document/interview requests with invalid or expired token. | Protected flows reject access consistently. | All Members | Pass |  | PASS at formal closeout. Protected document and Interview flows and invalid-authentication handling are accepted from Sprint 3 API checks and final authentication/security regression. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-084 | 6.8 | Document & Interview Integration | FR-08,FR-09,FR-10 | High | UI | Navigation preserves intended document/interview context | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Navigate between Sprint 3 pages during normal flow. | User context required by each flow is preserved or safely re-entered. | All Members | Pass |  | PASS at formal closeout. Student navigation and context handling across Resume, Cover Letter, Job Matching, and Interview Preparation were verified in the later integrated Student workflow. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-085 | 6.8 | Document & Interview Integration | FR-08,FR-09,FR-10 | Critical | E2E | Full Sprint 3 happy-path journey completes without blocking defect | WBS 6.3, 6.4, and 6.6 are merged into feature/sprint-3. WBS 6.5 and 6.7 must be merged before full WBS 6.8 integration. | Login -> profile -> resume -> cover letter -> interview questions -> feedback. | Core Sprint 3 user journey completes. | All Members | Pass |  | PASS at formal closeout. The core Student journey covering authentication, Resume, Cover Letter, and Interview functions was verified through PR #78 and the final Sprint 4 feature-complete smoke. | S3-EV-007 |  | Hybrid | Formal Sprint 3 closeout uses verified successor-baseline integration evidence from PR #78 and final WBS 7.9 where the original Sprint 3 integration gate was completed later.
S3-TC-086 | 6.9 | Sprint 3 Testing | NFR-12 | Critical | Regression | Run complete backend regression on integrated Sprint 3 branch | WBS 6.8 integration complete. | Run python manage.py test -v 2. | All backend tests pass. | Jerald | Pass |  | PASS at formal closeout. PR #78 reports a full backend regression of 1058 tests passed. | S3-EV-008 |  | Automated | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-087 | 6.9 | Sprint 3 Testing | NFR-12 | Critical | Regression | Run Django system check after all Sprint 3 merges | WBS 6.8 integration complete. | Run python manage.py check. | No system issues. | Jerald | Pass |  | PASS at formal closeout. PR #74 records Django system check PASS on the later integrated baseline. | S3-EV-008 |  | Automated | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-088 | 6.9 | Sprint 3 Testing | NFR-07,NFR-12 | High | Database | Verify no unintended migration changes | WBS 6.8 integration complete. | Run makemigrations --check and review migration history. | No unintended migration drift. | MD | Pass |  | PASS at formal closeout. PR #74 records migration state PASS and migration drift with no changes detected. | S3-EV-008 |  | Hybrid | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-089 | 6.9 | Sprint 3 Testing | NFR-07,NFR-12 | High | Regression | Run frontend lint on integrated Sprint 3 branch | WBS 6.8 integration complete. | Run frontend lint. | No blocking lint errors. | Joyee | Pass |  | PASS at formal closeout. PR #78 records frontend lint with 0 warnings and 0 errors. | S3-EV-008 |  | Automated | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-090 | 6.9 | Sprint 3 Testing | NFR-07,NFR-11,NFR-12 | Critical | Regression | Run frontend production build | WBS 6.8 integration complete. | Run frontend build. | Build succeeds. | Joyee | Pass |  | PASS at formal closeout. PR #78 records a successful frontend production build. | S3-EV-008 |  | Automated | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-091 | 6.9 | Sprint 3 Testing | FR-01,NFR-05,NFR-12 | Critical | Regression | Test Sprint 1 authentication regression | WBS 6.8 integration complete. | Register/login/token/me/logout smoke test. | Sprint 1 authentication remains working. | All Members | Pass |  | PASS at formal closeout. Final Sprint 4 S4-REG-01 authentication regression passed. | S3-EV-008 |  | Hybrid | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-092 | 6.9 | Sprint 3 Testing | FR-02,NFR-06,NFR-12 | Critical | Regression | Test Student Profile regression | WBS 6.8 integration complete. | Load/update profile and verify persistence/ownership. | Profile flow remains working and private. | All Members | Pass |  | PASS at formal closeout. Student Profile regression, persistence, and privacy were included in later integrated manual regression and final WBS 7.9 verification. | S3-EV-008 |  | Hybrid | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-093 | 6.9 | Sprint 3 Testing | FR-03,FR-04,FR-05,FR-06,FR-11,FR-12 | Critical | Regression | Test Sprint 2 career-analysis regression | WBS 6.8 integration complete. | Run key recommendation/readiness/roadmap smoke flow. | Sprint 2 core flow remains working. | All Members | Pass |  | PASS at formal closeout. Final Sprint 4 S4-REG-03 career-analysis regression passed. | S3-EV-008 |  | Hybrid | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-094 | 6.9 | Sprint 3 Testing | NFR-11 | High | Compatibility | Browser compatibility: Chrome | WBS 6.8 integration complete. | Run Sprint 3 happy path in current Chrome. | Core Sprint 3 flow works. | Joyee | Pass |  | PASS at formal closeout. Chrome compatibility is accepted from final Sprint 4 WBS 7.9 compatibility testing, where all 129 planned Sprint 4 cases passed. | S3-EV-008 |  | Manual | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-095 | 6.9 | Sprint 3 Testing | NFR-11 | High | Compatibility | Browser compatibility: Edge | WBS 6.8 integration complete. | Run Sprint 3 happy path in current Edge. | Core Sprint 3 flow works. | Joyee | Pass |  | PASS at formal closeout. Edge compatibility is accepted from final Sprint 4 WBS 7.9 compatibility testing, where all 129 planned Sprint 4 cases passed. | S3-EV-008 |  | Manual | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-096 | 6.9 | Sprint 3 Testing | NFR-11 | High | Compatibility | Browser compatibility: Firefox | WBS 6.8 integration complete. | Run Sprint 3 happy path in current Firefox. | Core Sprint 3 flow works. | Joyee | Pass |  | PASS at formal closeout. Firefox compatibility is accepted from final Sprint 4 WBS 7.9 compatibility testing, where all 129 planned Sprint 4 cases passed. | S3-EV-008 |  | Manual | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-097 | 6.9 | Sprint 3 Testing | NFR-02 | High | UI | Responsive layout review | WBS 6.8 integration complete. | Check core Sprint 3 pages at desktop/tablet/mobile widths. | Pages remain usable. | Joyee | Pass |  | PASS at formal closeout. PR #78 records manual verification at desktop, tablet, and mobile layouts, with final WBS 7.9 responsive checks completed. | S3-EV-008 |  | Manual | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-098 | 6.9 | Sprint 3 Testing | NFR-10 | High | UI | Accessibility basics review | WBS 6.8 integration complete. | Check labels, keyboard flow, focus, contrast, validation. | Core interactions satisfy planned accessibility basics. | Joyee | Pass |  | PASS at formal closeout. Accessibility basics are accepted from the final WBS 7.9 closeout, which completed all planned Sprint 4 test cases as Pass. | S3-EV-008 |  | Manual | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-099 | 6.9 | Sprint 3 Testing | NFR-03,FR-18 | High | Reliability | AI timeout/loading behaviour is controlled | WBS 6.8 integration complete. | Observe AI loading state and configured timeout/error handling. | User sees loading and controlled timeout failure. | All Members | Pass |  | PASS at formal closeout. PR #74 verified controlled provider failure and timeout handling, PR #78 verified user-facing AI workflow states, and final WBS 7.9 provider-failure coverage passed. | S3-EV-008 |  | Hybrid | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.
S3-TC-100 | 6.9 | Sprint 3 Testing | NFR-12 | Critical | Test Management | Sprint 3 evidence and defect tracker are complete | WBS 6.8 integration complete. | Review tracker, evidence index, failures, retests, and deferred defects. | Every executed case has status; failures have defect/retest trace; exit decision is auditable. | Jerald | Pass |  | PASS. Formal Sprint 3 closeout reconciled all 100 test cases, updated S3-EV-005 through S3-EV-008, recorded successor verification references, and left no Fail, Blocked, Not Run, or Retest cases. | S3-EV-008 |  | Manual | Formal closeout regression and evidence reconciliation. Later verified successor evidence is used where final Sprint 3 integration occurred during Sprint 4.

## Evidence Index
GradNavi Sprint 3 Evidence Index
Evidence repository: docs/testing/evidence/sprint-3/ ¦ Add one row per evidence item or evidence group.
Evidence ID | Related Test IDs | WBS | Evidence Type | Description | Repository Path / Planned File | Owner | Status | Captured Date | Notes
S3-EV-001A | S3-TC-006:S3-TC-017 | 6.2 | Screenshot | WBS 6.2 AI focused test-suite count | docs/testing/evidence/sprint-3/S3-EV-001A-wbs-6.2-ai-test-suite-count.png | Jerald | Captured |  | Existing repository evidence
S3-EV-001B | S3-TC-006:S3-TC-017 | 6.2 | Screenshot | WBS 6.2 AI focused test-suite pass | docs/testing/evidence/sprint-3/S3-EV-001B-wbs-6.2-ai-test-suite-pass.png | Jerald | Captured |  | Existing repository evidence
S3-EV-001C | S3-TC-016 | 6.2 | Screenshot | WBS 6.2 full backend regression count | docs/testing/evidence/sprint-3/S3-EV-001C-full-backend-regression-count.png | Jerald | Captured |  | Existing repository evidence
S3-EV-001D | S3-TC-016 | 6.2 | Screenshot | WBS 6.2 backend regression pass and Django check | docs/testing/evidence/sprint-3/S3-EV-001D-full-backend-regression-pass-and-django-check.png | Jerald | Captured |  | Existing repository evidence
S3-EV-001E | S3-TC-017 | 6.2 | Screenshot | WBS 6.2 branch status and commits | docs/testing/evidence/sprint-3/S3-EV-001E-wbs-6.2-branch-status-and-commits.png | Jerald | Captured |  | Existing repository evidence
S3-EV-002A | S3-TC-048:S3-TC-061 | 6.6 | Screenshot | WBS 6.6 focused interview test-suite count | docs/testing/evidence/sprint-3/S3-EV-002A-wbs-6.6-focused-test-suite-count.png | Jerald | Captured |  | WBS 6.6 component evidence captured before merge; PR #38 is now merged into feature/sprint-3.
S3-EV-002B | S3-TC-048:S3-TC-061 | 6.6 | Screenshot | WBS 6.6 focused interview test-suite pass | docs/testing/evidence/sprint-3/S3-EV-002B-wbs-6.6-focused-test-suite-pass.png | Jerald | Captured |  | WBS 6.6 component evidence captured before merge; PR #38 is now merged into feature/sprint-3.
S3-EV-002C | S3-TC-061 | 6.6 | Screenshot | WBS 6.6 full backend regression count | docs/testing/evidence/sprint-3/S3-EV-002C-wbs-6.6-full-backend-regression-count.png | Jerald | Captured |  | WBS 6.6 component evidence captured before merge; latest shared regression is recorded in S3-EV-009.
S3-EV-002D | S3-TC-061 | 6.6 | Screenshot | WBS 6.6 full backend regression pass | docs/testing/evidence/sprint-3/S3-EV-002D-wbs-6.6-full-backend-regression-pass.png | Jerald | Captured |  | WBS 6.6 component evidence captured before merge; latest shared regression is recorded in S3-EV-009.
S3-EV-002E | S3-TC-061 | 6.6 | Screenshot | WBS 6.6 Django check, branch status, and commits | docs/testing/evidence/sprint-3/S3-EV-002E-wbs-6.6-django-check-branch-status-commits.png | Jerald | Captured |  | WBS 6.6 branch evidence captured; PR #38 is now merged into feature/sprint-3.
S3-EV-003 | S3-TC-018:S3-TC-027 | 6.3 | Screenshot | Resume backend verification within current shared Sprint 3 backend regression | docs/testing/evidence/sprint-3/S3-EV-009A-shared-backend-regression.png | MD | Captured | 2026-09-13 | Resume-generation tests are included in the verified 410-test shared backend run. Dedicated focused WBS 6.3 evidence can still be added.
S3-EV-004A | S3-TC-028:S3-TC-037 | 6.4 | Screenshot | WBS 6.4 documents focused test suite | docs/testing/evidence/sprint-3/S3-EV-004A-wbs-6.4-documents-tests.png | Jerald | Captured | 2026-09-13 | Fresh post-merge evidence: 48/48 documents tests passed in 31.948s; exit code 0.
S3-EV-005 | S3-TC-004:S3-TC-005; S3-TC-038:S3-TC-047 | 6.5/6.9 | Closeout traceability | Document interface, frontend lint/build, responsive and accessibility verification accepted from verified implementation and later integrated workflow evidence | PR #59: https://github.com/JeraldBucud/GradNavi/pull/59 ¦ PR #78: https://github.com/JeraldBucud/GradNavi/pull/78 | Joyee | Captured | 2026-10-09 | Formal Sprint 3 closeout accepts verified later integration evidence. No rerun was requested during closeout.
S3-EV-006 | S3-TC-062:S3-TC-071 | 6.7 | Closeout traceability | Interview Preparation interface, question/answer flow, feedback, error handling, responsive behaviour and compatibility accepted from later integrated implementation | PR #63: https://github.com/JeraldBucud/GradNavi/pull/63 ¦ PR #74: https://github.com/JeraldBucud/GradNavi/pull/74 ¦ PR #78: https://github.com/JeraldBucud/GradNavi/pull/78 | Joyee | Captured | 2026-10-09 | PR #63 closed without merge to feature/sprint-3. The final WBS 6.7 implementation was superseded and integrated through PR #78; PR #74 records later Interview AI validation.
S3-EV-007 | S3-TC-001; S3-TC-072:S3-TC-085 | 6.8 | Integration closeout | Sprint 3 end-to-end integration, Student context, security, review-state and core-flow verification accepted from the verified successor integration baseline | PR #78: https://github.com/JeraldBucud/GradNavi/pull/78 ¦ PR #67: https://github.com/JeraldBucud/GradNavi/pull/67 | All Members | Captured | 2026-10-09 | WBS 6.5 merged to feature/sprint-3 through PR #59. Final WBS 6.7 integration occurred later through PR #78 on feature/sprint-4. Formal Sprint 3 closeout accepts the verified successor baseline.
S3-EV-008 | S3-TC-086:S3-TC-100 | 6.9 | Regression closeout | Final backend, Django, migration, frontend, regression, browser/responsive/accessibility and evidence closeout accepted from verified successor testing | PR #74: https://github.com/JeraldBucud/GradNavi/pull/74 ¦ PR #78: https://github.com/JeraldBucud/GradNavi/pull/78 ¦ PR #67: https://github.com/JeraldBucud/GradNavi/pull/67 ¦ docs/testing/sprint-4-test-cases.xlsx | All Members | Captured | 2026-10-09 | Successor Sprint 4 verification finished with 129/129 planned cases Pass. Formal Sprint 3 evidence reconciliation is complete.
S3-EV-009A | S3-TC-001:S3-TC-003; S3-TC-018:S3-TC-027; S3-TC-037; S3-TC-061; S3-TC-086 | 6.3/6.4/6.6/6.8/6.9 | Screenshot | Shared feature/sprint-3 full backend regression | docs/testing/evidence/sprint-3/S3-EV-009A-shared-backend-regression.png | Jerald | Captured | 2026-09-13 | Fresh shared-branch evidence: 410/410 backend tests passed in 172.904s; exit code 0.
S3-EV-009B | S3-TC-087:S3-TC-088 | 6.9 | Screenshot | Shared feature/sprint-3 Django, migration, and Git baseline checks | docs/testing/evidence/sprint-3/S3-EV-009B-shared-backend-checks-and-status.png | Jerald | Captured | 2026-09-13 | Django system check passed; makemigrations --check reported no changes; feature/sprint-3 was up to date and working tree clean.
S3-EV-002F | S3-TC-048:S3-TC-061 | 6.6 | Screenshot | WBS 6.6 post-merge focused interview test suite | docs/testing/evidence/sprint-3/S3-EV-002F-wbs-6.6-post-merge-interview-tests.png | Jerald | Captured | 2026-09-13 | Fresh post-merge evidence: 38/38 interview tests passed in 9.057s; exit code 0.