## Summary
GradNavi WBS 8.3 Security and Permission Test Tracker
Tracker Metadata | Value | Status | Count
WBS | 8.3 Security and Permission Testing | Total | 32
Owner | Jerald | Not Run | 0
Branch | jerald/wbs-8.3-frontend-permission-follow-up | Pass | 30
Automated regression | 330 tests PASS | Fail | 0
Automated evidence | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Blocked | 0
Current phase | Local WBS 8.3 security execution complete: 30 Pass, 0 Blocked, 2 Deferred deployment reviews. S5-SEC-FE-01 passed after WBS 7.7 integration. | Deferred | 2
Execution Method | Count | Evidence Layer | Count
POSTMAN + AUTOMATED | 21 | Automated Pass | 27
AUTOMATED + STATIC | 6 | Manual/Review Pass | 29
REPOSITORY REVIEW | 2 | Manual/Review Pending | 0
BROWSER / INTEGRATION | 1 | Manual/Review Blocked | 1
DEPLOYMENT REVIEW | 2 | Manual/Review Deferred | 2
Tracker rule: a WBS test case becomes Pass only after every required evidence layer for that case passes.

## Test Cases
Test Case ID | Security Area | Test Objective | Expected Result | Evidence Method | Automated Test Reference | HTTP Method | Endpoint | Authentication State | Expected HTTP Status | Automated Evidence | Manual / Review Evidence | Actual HTTP Status | Actual Result | Status | Tester | Execution Date | Evidence File | Defect ID | Retest Status | Notes | Source / Implementation Files
S5-SEC-AUTH-01 | Authentication | Verify valid credentials authenticate and return JWT access and refresh tokens with safe user fields only. | Valid Student login returns HTTP 200, access and refresh JWTs, and safe user fields without password or privileged-field leakage. | POSTMAN + AUTOMATED | LoginAPITests.test_successful_login_returns_tokens_and_safe_user_information; LoginAPITests.test_successful_login_issues_valid_jwt_tokens | POST | /api/v1/auth/login/ | Unauthenticated | 200 | Pass | Pass | 200 | Valid Student login returned HTTP 200 with access and refresh JWTs and safe user fields only. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-01-valid-student-login-pass.png |  | Not Required | Postman validation passed 6/6. | backend/accounts/views.py; backend/accounts/serializers.py; backend/accounts/tests.py
S5-SEC-AUTH-02 | Authentication | Verify wrong password and unknown email return the same safe authentication error. | Wrong password and unknown email both return HTTP 401 with the same safe invalid-credentials error and no account-discovery detail. | POSTMAN + AUTOMATED | LoginAPITests.test_wrong_password_is_rejected_with_safe_error; LoginAPITests.test_nonexistent_email_is_rejected_with_same_safe_error; LoginAPITests.test_wrong_password_and_nonexistent_email_return_same_error | POST | /api/v1/auth/login/ | Unauthenticated | 401 | Pass | Pass | 401 for both negative login checks | Wrong password and unknown email both returned the same safe HTTP 401 invalid-credentials response without account information leakage. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-02A-wrong-password-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-02B-unknown-email-rejected-pass.png |  | Not Required | Wrong-password and unknown-email Postman checks passed. | backend/accounts/views.py; backend/accounts/tests.py
S5-SEC-AUTH-03 | Authentication | Verify protected APIs reject missing, malformed, invalid, or inappropriate authentication tokens. | Protected endpoint returns HTTP 401 for missing Bearer token, malformed token, and refresh token used as access authentication. | POSTMAN + AUTOMATED | CurrentUserAPITests.test_missing_authorization_header_is_rejected; CurrentUserAPITests.test_malformed_token_is_rejected; CurrentUserAPITests.test_refresh_token_cannot_authenticate_current_user_endpoint | GET | /api/v1/auth/me/ | Missing / invalid / refresh-as-access | 401 | Pass | Pass | 401 for all three rejection checks | Missing authorization, malformed access token, and refresh-token-as-access attempts were rejected with safe HTTP 401 responses. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-03A-missing-authorization-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-03B-malformed-access-token-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-03C-refresh-token-rejected-as-access-pass.png |  | Not Required | All protected-endpoint authentication rejection checks passed. | backend/accounts/views.py; backend/accounts/tests.py
S5-SEC-AUTH-04 | Authentication | Verify refresh-token rotation works and the previous refresh token is rejected after rotation. | Valid refresh returns HTTP 200 with rotated tokens. Reuse of the previous refresh token returns HTTP 401. The new refresh token remains usable. | POSTMAN + AUTOMATED | TokenRefreshAPITests.test_valid_refresh_token_succeeds_and_returns_rotated_tokens; TokenRefreshAPITests.test_original_refresh_token_cannot_be_reused_after_rotation; TokenRefreshAPITests.test_new_rotated_refresh_token_can_be_used_for_another_refresh | POST | /api/v1/auth/token/refresh/ | Refresh token | 200 then 401 on old-token reuse | Pass | Pass | 200, 401, 200 | Refresh rotation succeeded, the original refresh token was rejected after rotation, and the rotated refresh token remained usable. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-04A-refresh-token-rotation-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-04B-original-refresh-token-reuse-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-04C-rotated-refresh-token-works-pass.png |  | Not Required | JWT refresh-token rotation contract verified. | backend/accounts/urls.py; backend/gradnavi/settings.py; backend/accounts/tests.py
S5-SEC-AUTH-05 | Authentication | Verify logout blacklists the submitted refresh token and follows the documented access-token expiry behaviour. | Authenticated logout returns HTTP 200. The submitted refresh token is rejected with HTTP 401 afterwards. Existing access token behaviour matches the documented expiry model. | POSTMAN + AUTOMATED | LogoutAPITests.test_successful_logout_blacklists_submitted_refresh_token; LogoutAPITests.test_existing_access_token_remains_usable_until_expiry_after_logout | POST | /api/v1/auth/logout/ | Student Bearer + refresh token body | 200; refresh reuse 401 | Pass | Pass | 200, 401, 200 | Logout succeeded, the submitted refresh token was blacklisted and rejected, and the already-issued access token remained valid until expiry. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-05A-student-logout-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-05B-logged-out-refresh-token-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-05C-existing-access-token-remains-valid-pass.png |  | Not Required | Logout and documented access-token expiry behaviour verified. | backend/accounts/views.py; backend/accounts/tests.py; backend/gradnavi/settings.py
S5-SEC-AUTH-06 | Authentication | Verify password reset and authenticated password change enforce approved validation without exposing account-sensitive information. | Password-reset request uses a safe non-enumerating response. Password change requires authentication, correct current password, matching confirmation, and an accepted new password. | POSTMAN + AUTOMATED | PasswordResetAPITests.test_unknown_email_request_returns_same_safe_response_and_sends_no_email; PasswordResetAPITests.test_reset_request_response_does_not_expose_uid_or_token; PasswordChangeAPITests.test_valid_password_change_succeeds; PasswordChangeAPITests.test_incorrect_current_password_is_rejected; PasswordChangeAPITests.test_weak_new_password_is_rejected | POST | /api/v1/auth/password/reset/; /api/v1/auth/password/change/ | Unauthenticated reset; Student Bearer change | Safe reset response; 200 valid change; 400 invalid change | Pass | Pass | 200, 200, 400, 400, 200, 200 | Password reset used safe non-enumerating responses. Incorrect current password and weak new password were rejected. Valid password change succeeded and the original Student password was restored. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06A-password-reset-safe-response-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06B-unknown-email-reset-safe-response-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06C-incorrect-current-password-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06D-weak-new-password-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06E-valid-password-change-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06F-original-password-restored-pass.png |  | Not Required | Original Student test password restored after valid-change verification. | backend/accounts/views.py; backend/accounts/serializers.py; backend/accounts/tests.py
S5-SEC-RBAC-01 | Authorization / RBAC | Verify unauthenticated requests receive 401 for Administrator endpoints. | Representative Administrator list and detail endpoints return HTTP 401 without authentication. | POSTMAN + AUTOMATED | AdministrationPermissionTests.test_unauthenticated_users_cannot_access_admin_endpoints; AdministrationPermissionTests.test_non_admins_cannot_access_admin_detail_endpoints | GET | /api/v1/administration/users/; /api/v1/administration/audit-records/ | Unauthenticated | 401 | Pass | Pass | 401 for collection and detail requests | Unauthenticated requests to Administrator collection and user-detail endpoints were rejected with HTTP 401 and exposed no protected data. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-01A-unauthenticated-admin-users-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-01B-unauthenticated-admin-user-detail-rejected-pass.png |  | Not Required | Unauthenticated Administrator endpoint protection verified. | backend/administration/permissions.py; backend/administration/views.py; backend/administration/tests.py
S5-SEC-RBAC-02 | Authorization / RBAC | Verify Student accounts receive 403 for Administrator list and detail endpoints. | Representative Administrator endpoints return HTTP 403 when called with a Student token. | POSTMAN + AUTOMATED | AdministrationPermissionTests.test_students_cannot_access_admin_endpoints; AdministrationPermissionTests.test_non_admins_cannot_access_admin_detail_endpoints | GET | /api/v1/administration/users/; /api/v1/administration/analytics/ | Student Bearer | 403 | Pass | Pass | 403 for collection and detail requests | Authenticated Student requests to Administrator collection and detail endpoints were rejected with permission_denied and HTTP 403. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-02A-student-admin-users-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-02B-student-admin-user-detail-rejected-pass.png |  | Not Required | Student-to-Administrator RBAC boundary verified. | backend/administration/permissions.py; backend/administration/tests.py
S5-SEC-RBAC-03 | Authorization / RBAC | Verify Student accounts cannot perform Administrator create, update, delete, role, status, report-review, analytics, or audit operations. | Student requests to Administrator mutation and protected read endpoints are denied with HTTP 403. | POSTMAN + AUTOMATED | AdministrationPermissionTests.test_student_cannot_create_career; AdminUserRoleStatusAuditTests.test_student_cannot_change_role_or_status; AdminLearningResourceReportReviewTests.test_student_cannot_access_report_detail_or_update | POST/PATCH/DELETE/GET | /api/v1/administration/* | Student Bearer | 403 | Pass | Pass | 403 for all attempted Administrator operations | Student create, update, delete, role, status, report-review, analytics, and audit operations were rejected with HTTP 403. Temporary report and learning-resource records were removed after testing. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03A-student-admin-career-create-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03B-student-admin-role-change-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03C-student-admin-status-change-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03D-student-admin-analytics-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03E-student-admin-audit-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03F1-student-admin-report-detail-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03F2-student-admin-report-update-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03G-student-admin-resource-update-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03H-student-admin-resource-delete-rejected-pass.png |  | Not Required | All planned RBAC-03 Student denial operations passed. Temporary test records were cleaned up. | backend/administration/permissions.py; backend/administration/views.py; backend/administration/tests.py
S5-SEC-RBAC-04 | Authorization / RBAC | Verify general Administrator user editing cannot modify role or active status through the general user endpoint. | General user-detail update preserves role and active status as server-controlled fields. | POSTMAN + AUTOMATED | AdminUserManagementTests.test_admin_cannot_change_role_or_active_status | PATCH | /api/v1/administration/users/<id>/ | Administrator Bearer | 200 with role/status unchanged | Pass | Pass | 200 | General Administrator user-detail PATCH returned HTTP 200 while preserving role=admin and is_active=true. Sensitive authentication data was not exposed. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-04-general-admin-user-edit-protects-role-status-pass.png |  | Not Required | General user-edit endpoint preserved server-controlled role and active status. Postman checks passed 6/6. | backend/administration/serializers.py; backend/administration/views.py; backend/administration/tests.py
S5-SEC-RBAC-05 | Authorization / RBAC | Verify role and active-status changes use dedicated Administrator-only endpoints and reject invalid role values. | Valid dedicated role/status changes succeed for an Administrator. Invalid role values are rejected. Student and unauthenticated callers are denied. | POSTMAN + AUTOMATED | AdminUserRoleStatusAuditTests.test_admin_can_change_user_role_through_dedicated_endpoint; AdminUserRoleStatusAuditTests.test_admin_can_change_user_active_status_through_dedicated_endpoint; AdminUserRoleStatusAuditTests.test_invalid_role_change_is_rejected | PATCH | /api/v1/administration/users/<id>/role/; /api/v1/administration/users/<id>/status/ | Administrator Bearer | 200 valid; 400 invalid role | Pass | Pass | 200, 200, 400 | Dedicated Administrator role and status endpoints accepted valid changes. An invalid role value returned a controlled HTTP 400 validation response. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05A-dedicated-admin-role-change-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05B-dedicated-admin-status-change-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05C-invalid-admin-role-change-rejected-pass.png |  | Not Required | Dedicated role/status endpoint contract verified. Invalid role validation passed 6/6. | backend/administration/serializers.py; backend/administration/views.py; backend/administration/tests.py
S5-SEC-RBAC-06 | Authorization / RBAC | Verify audit and analytics endpoints are Administrator-only, audit records are read-only, and responses do not expose unnecessary Student information. | Administrator reads succeed. Student access is denied. Audit mutation is not allowed. Analytics and audit responses omit unnecessary Student identity information. | POSTMAN + AUTOMATED | AdminAuditRecordTests.test_admin_can_list_and_retrieve_audit_records; AdminAuditRecordTests.test_audit_records_endpoint_is_read_only; AdminAuditRecordTests.test_audit_response_does_not_expose_user_email; AdminAnalyticsTests.test_analytics_response_exposes_no_student_data | GET + write attempt | /api/v1/administration/audit-records/; /api/v1/administration/analytics/ | Administrator / Student | 200 admin; 403 student; 405 audit write | Pass | Pass | 200, 200, 405, 200 | Administrator audit list/detail and analytics reads succeeded. Audit write was rejected with HTTP 405. Responses excluded unnecessary identity, password, and token values. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06A-administrator-audit-records-list-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06B-administrator-audit-record-detail-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06C-audit-records-endpoint-read-only-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06D-administrator-analytics-response-safe-pass.png |  | Not Required | Audit read-only behaviour and analytics response minimisation verified. | backend/administration/views.py; backend/administration/serializers.py; backend/administration/tests.py
S5-SEC-OWN-01 | Object Ownership | Verify Student Profile GET resolves only the authenticated user's profile and does not expose another Student profile. | Authenticated GET returns only the caller's Student Profile. Cross-user profile data is absent. | POSTMAN + AUTOMATED | StudentProfileReadAPITests.test_get_uses_authenticated_user_and_does_not_leak_cross_user_data | GET | /api/v1/profile/ | Student Bearer | 200 | Pass | Pass | 200 | Student Profile GET used the authenticated Student context. Cross-user query identifiers did not expose another profile, career goal, or ownership fields. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-01-student-profile-ignores-cross-user-identifiers-pass.png |  | Not Required | Authenticated-profile isolation passed 6/6. | backend/profiles/views.py; backend/profiles/tests.py
S5-SEC-OWN-02 | Object Ownership | Verify Student Profile PATCH rejects ownership spoofing through identifiers, nested records, query parameters, or protected fields. | Ownership identifiers and cross-user nested record IDs are rejected. Another Student profile is not modified. | POSTMAN + AUTOMATED | StudentProfilePatchAPITests.test_client_supplied_ownership_identifiers_are_rejected; StudentProfilePatchAPITests.test_cross_user_nested_id_is_rejected_without_modifying_other_profile; StudentProfilePatchAPITests.test_authenticated_user_cannot_patch_another_profile_with_query_parameters | PATCH | /api/v1/profile/ | Student Bearer | 400 | Pass | Pass | 400, 400, 200 | Client-supplied user_id and cross-user CareerGoal ID were rejected. Cross-user query parameters could not redirect profile update. Database verification confirmed caller and cross-user data stayed isolated. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02A-client-supplied-user-id-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02B-cross-user-career-goal-id-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02C-cross-user-query-parameters-cannot-redirect-profile-update-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02-database-state-verification-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02-temporary-users-cleanup-pass.png |  | Not Required | Ownership spoofing rejected and database state verified. Temporary ownership users were removed after testing. | backend/profiles/views.py; backend/profiles/tests.py
S5-SEC-OWN-03 | Object Ownership | Verify Career Recommendation, Learning Resource, Roadmap, and related Student guidance operations derive Student context from the authenticated user. | Guidance services obtain Student Profile context from request.user rather than a client-selected Student identity. | AUTOMATED + STATIC | RecommendationAPITests.test_authenticated_user_profile_is_used_exclusively; LearningRoadmapAPITests.test_student_profile_is_derived_from_request_user | N/A | /api/v1/recommendations/; /api/v1/learning-resources/; /api/v1/roadmaps/ | Authenticated Student context | N/A for static layer | Pass | Pass | N/A (automated/static) | Targeted ownership tests passed and static review confirmed Recommendation, Learning/Roadmap, and related guidance paths derive Student Profile context from request.user rather than client-supplied identity. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-targeted-automated-tests-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-static-recommendation-ownership-check.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-static-learning-roadmap-ownership-check.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-static-query-ownership-check.png |  | Not Required | Targeted automated coverage and static request.user ownership review completed. | backend/careers/views.py; backend/careers/tests.py
S5-SEC-OWN-04 | Object Ownership | Verify Job Description Matching derives the Student Profile from request.user rather than a client-supplied profile identity. | Valid job-match request uses the authenticated Student Profile and does not accept another Student profile identity. | POSTMAN + AUTOMATED | JobDescriptionMatchAPITests.test_authenticated_profile_ownership | POST | /api/v1/careers/job-match/ | Student Bearer | 200 valid request | Pass | Pass | 200, 400 | Valid Job Match used the authenticated Student Profile. A client-supplied profile identity field was rejected with HTTP 400. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-04A-job-match-uses-authenticated-student-profile-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-04B-job-match-rejects-client-supplied-profile-identity-pass.png |  | Not Required | Job Match authenticated-profile ownership and selector rejection verified. | backend/careers/views.py; backend/careers/test_job_description_matching.py
S5-SEC-OWN-05 | Object Ownership | Verify Resume and Cover Letter generation use the authenticated user's profile and reject attempts to select another Student profile or supply protected prompt controls. | Valid generation uses the caller's profile. Client-supplied Student profile IDs, user IDs, profile prompts, or system prompts are rejected where prohibited. | POSTMAN + AUTOMATED | ResumeGenerationAPITests.test_authenticated_user_profile_is_used_exclusively; CoverLetterGenerationAPITests.test_authenticated_user_profile_is_used_exclusively; CoverLetterGenerationAPITests.test_client_cannot_select_another_student_profile; CoverLetterGenerationAPITests.test_student_profile_id_is_rejected | POST | /api/v1/documents/resume/generate/; /api/v1/documents/cover-letter/generate/ | Student Bearer | 200 valid; 400 protected/spoof fields | Pass | Pass | 400, 400 | Resume and Cover Letter generation rejected client-supplied Student Profile selectors. Automated coverage confirms generation derives profile context from the authenticated user. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-05A-resume-rejects-client-supplied-student-profile-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-05B-cover-letter-rejects-client-supplied-student-profile-pass.png |  | Not Required | Protected Student Profile selector rejection verified for both document-generation endpoints. | backend/documents/views.py; backend/documents/tests.py
S5-SEC-OWN-06 | Object Ownership | Verify Interview History returns only the authenticated user's records and new history records bind ownership to request.user. | GET returns only caller history. POST binds the new session to the caller. Client-supplied user ownership is rejected. | POSTMAN + AUTOMATED | InterviewHistoryAPITests.test_post_creates_owned_session_metadata; InterviewHistoryAPITests.test_get_returns_only_authenticated_user_history; InterviewHistoryAPITests.test_user_id_is_rejected | GET/POST | /api/v1/interviews/history/ | Student Bearer | 200 GET; 201 POST; 400 spoofed owner | Pass | Pass | 201, 200, 400, 200 | Student A created and retrieved its own Interview History. Client-supplied user_id was rejected. Student B could not retrieve Student A history. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06A-student-a-creates-owned-interview-history-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06B-student-a-sees-own-interview-history-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06C-client-supplied-interview-history-user-id-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06D-student-b-cannot-see-student-a-interview-history-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06-student-b-fixture-created.png |  | Not Required | Interview History ownership binding and cross-user isolation verified. | backend/interviews/views.py; backend/interviews/tests.py
S5-SEC-IN-01 | Input Protection | Verify clients cannot set protected role, ownership, system-prompt, profile-identity, or server-controlled values. | Protected fields are rejected or ignored according to the documented endpoint contract. Server-controlled identity and privilege values remain unchanged. | POSTMAN + AUTOMATED | RegistrationAPITests.test_public_registration_cannot_create_privileged_user; AccountSettingsAPITests.test_email_and_role_are_read_only; CoverLetterGenerationAPITests.test_user_id_is_rejected; CoverLetterGenerationAPITests.test_profile_prompt_and_system_prompt_fields_are_rejected; InterviewRequestSerializerTests.test_question_request_rejects_user_id; InterviewRequestSerializerTests.test_question_request_rejects_client_prompt | POST/PATCH | Representative auth, settings, document and interview endpoints | Unauthenticated / Student Bearer | 400 or safe read-only preservation | Pass | Pass | 201, 200, 400, 400, 400, 400 | Registration could not create an Administrator. Account settings preserved protected email/role. Document and Interview endpoints rejected client-supplied ownership, profile, prompt, and system-prompt controls. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-IN-01A-public-registration-cannot-create-privileged-user-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01B-account-settings-protect-email-and-role-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01C-cover-letter-rejects-client-supplied-user-id-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01D-cover-letter-rejects-protected-prompt-controls-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01E-interview-questions-reject-client-supplied-user-id-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01F-interview-questions-reject-client-supplied-prompt-pass.png |  | Not Required | Server-controlled role, ownership, profile identity, and prompt boundaries verified. | backend/accounts/serializers.py; backend/documents/serializers.py; backend/interviews/serializers.py
S5-SEC-IN-02 | Input Protection | Verify invalid values, invalid identifiers, invalid file content, invalid role values, and unsupported data produce controlled validation responses. | Invalid inputs return controlled HTTP 400 validation responses without unsafe internal details. | POSTMAN + AUTOMATED | AdminUserRoleStatusAuditTests.test_invalid_role_change_is_rejected; AccountSettingsAPITests.test_gif_profile_photo_is_rejected; AccountSettingsAPITests.test_profile_photo_over_five_mb_is_rejected; StudentProfilePatchAPITests.test_invalid_proficiency_and_missing_reference_are_rejected; JobDescriptionMatchAPITests.test_unknown_fields_rejected | POST/PATCH | Representative administration, settings, profile and job-match endpoints | Student / Administrator Bearer | 400 | Pass | Pass | 400 for all invalid-input checks | Invalid Administrator role, GIF upload, oversized profile photo, invalid skill proficiency, missing Interest reference, and unknown Job Match profile field all produced controlled HTTP 400 validation responses. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05C-invalid-admin-role-change-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02A-gif-profile-photo-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02B-oversized-profile-photo-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02C-invalid-skill-proficiency-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02D-missing-interest-reference-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02E-job-match-rejects-unknown-student-profile-field-pass.png |  | Not Required | RBAC-05C is reused as the mapped invalid-role evidence. All remaining IN-02 invalid-input checks passed. | backend/accounts/serializers.py; backend/administration/serializers.py; backend/profiles/serializers.py
S5-SEC-AI-01 | AI Privacy / Trust | Verify AI Student Profile context is restricted to the approved allowlist. | Only approved Student Profile areas are mapped into AI context. | AUTOMATED + STATIC | ResumeGenerationServiceTests.test_approved_profile_context_reaches_provider_through_privacy_mapper; CoverLetterGenerationServiceTests.test_approved_profile_context_reaches_provider_through_privacy_mapper | N/A | N/A | N/A | N/A | Pass | Pass | N/A (automated/static) | Resume and Cover Letter privacy-mapper tests passed. Static review confirmed AI_PROFILE_ALLOWLIST contains only skills, education, experience, projects, and career_goals. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AI-01-approved-profile-context-privacy-mapper-tests-pass.png |  | Not Required | Mapped provider-context tests passed 2/2. Static review of backend/ai_services/safety/privacy.py confirmed the five-section allowlist. | backend/ai_services/safety/privacy.py; backend/documents/tests.py
S5-SEC-AI-02 | AI Privacy / Trust | Verify sensitive profile and account fields are excluded from AI profile context. | User IDs, StudentProfile IDs, email, role, password data, JWT data, internal identifiers, personality responses, interests, project URLs, and database timestamps do not reach the provider profile context. | AUTOMATED + STATIC | ResumeGenerationServiceTests.test_private_profile_fields_are_not_exposed_to_provider_prompt; CoverLetterGenerationServiceTests.test_private_profile_fields_are_not_exposed_to_provider_prompt | N/A | N/A | N/A | N/A | Pass | Pass | N/A (automated/static) | Resume and Cover Letter tests confirmed private profile values are not exposed to provider prompts. Static privacy mapper excludes identity, credentials, interests, personality responses, project URLs, timestamps, and internal identifiers. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AI-02-private-profile-fields-not-exposed-to-provider-prompt-pass.png |  | Not Required | Mapped private-field provider-prompt tests passed 2/2. Static exclusion rules reviewed. | backend/ai_services/safety/privacy.py; backend/documents/tests.py
S5-SEC-AI-03 | AI Privacy / Trust | Verify AI provider failures and invalid generated responses return controlled API errors without provider credentials or internal exception details. | Provider timeout, unavailability, semantic validation failure, and response validation failure return controlled 502/503 responses without secret or stack-trace leakage. | AUTOMATED + STATIC | ResumeGenerationAPITests.test_shared_ai_service_failure_returns_503; ResumeGenerationAPITests.test_response_validation_failure_is_sanitized_503; CoverLetterGenerationAPITests.test_provider_unavailable_returns_503; InterviewQuestionAPITests.test_provider_timeout_returns_503; InterviewQuestionAPITests.test_semantic_validation_failure_returns_controlled_502; InterviewFeedbackAPITests.test_provider_timeout_returns_503 | N/A | AI-backed document and interview endpoints | Authenticated Student | Controlled 502/503 in automated failure simulations | Pass | Pass | 502/503 (automated failure simulations) | All six mapped provider-failure and invalid-response tests passed. Static review confirmed controlled errors and no provider secret, stack trace, prompt, credential, or Student-content leakage. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AI-03-controlled-ai-provider-failure-tests-pass.png |  | Not Required | Mapped AI failure tests passed 6/6. Static review confirmed safe 502/503 handling, sanitised error envelopes, and safe validation logging. | backend/gradnavi/exceptions.py; backend/documents/tests.py; backend/interviews/tests.py
S5-SEC-AI-04 | AI Privacy / Trust | Verify user-supplied content stays separate from backend-controlled AI instructions and AI output does not replace backend authorization or deterministic scoring. | Untrusted content cannot become trusted system instruction. Job matching and scoring authority remains backend-controlled and deterministic where designed. | AUTOMATED + STATIC | CoverLetterGenerationServiceTests.test_job_description_instructions_do_not_become_trusted_instructions; InterviewQuestionServiceTests.test_question_context_preserves_trust_boundary; InterviewFeedbackServiceTests.test_feedback_context_is_untrusted; JobDescriptionMatchAPITests.test_job_matching_output_is_independent_of_text_ai_provider | N/A | N/A | N/A | N/A | Pass | Pass | N/A (automated/static) | Four mapped trust-boundary tests passed. User-supplied Job Description, target role, interview question, and Student answer remained untrusted content. Job Match scoring remained independent of the text AI provider. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AI-04-untrusted-content-and-deterministic-scoring-tests-pass.png |  | Not Required | Mapped trust-boundary and deterministic-scoring tests passed 4/4. | backend/ai_services/prompts; backend/documents/tests.py; backend/interviews/tests.py
S5-SEC-AUD-01 | Audit / Error Protection | Verify supported Administrator mutations create the required audit records. | An approved Administrator mutation succeeds and the corresponding audit action becomes available through the Administrator audit endpoint. | POSTMAN + AUTOMATED | AdminAuditRecordTests.test_career_create_update_and_delete_create_audit_records; AdminAuditRecordTests.test_learning_resource_report_status_change_creates_audit_record | POST/PATCH then GET | /api/v1/administration/careers/ then /api/v1/administration/audit-records/ | Administrator Bearer | 201/200 mutation then 200 audit read | Pass | Pass | 201/200/204 mutations; 200 audit reads | Administrator Career create, update, and delete operations produced matching audit records. Learning Resource Report status transition from open to resolved produced the expected status_changed audit record and metadata. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01-administrator-mutations-create-audit-records-tests-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01A-administrator-creates-audited-career-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01B-career-creation-audit-record-exists-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01C-administrator-updates-audited-career-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01D-career-update-audit-record-exists-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01E-administrator-deletes-audited-career-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01F-career-deletion-audit-record-exists-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01G-administrator-resolves-learning-resource-report-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01H-learning-resource-report-status-audit-record-exists-pass.png |  | Not Required | Mapped automated tests passed 2/2. Postman evidence verified Career audit lifecycle and Learning Resource Report status-change metadata. | backend/administration/audit.py; backend/administration/views.py; backend/administration/tests.py
S5-SEC-AUD-02 | Audit / Error Protection | Verify audit responses are Administrator-only, read-only, and exclude unnecessary identity or credential information. | Administrator GET succeeds, Student access is denied, audit modification is rejected, and audit response does not expose user email or credential data. | POSTMAN + AUTOMATED | AdminAuditRecordTests.test_admin_can_list_and_retrieve_audit_records; AdminAuditRecordTests.test_audit_records_endpoint_is_read_only; AdminAuditRecordTests.test_audit_response_does_not_expose_user_email | GET + write attempt | /api/v1/administration/audit-records/ | Administrator / Student | 200 admin; 403 student; 405 write | Pass | Pass | 200 admin; 403 student; 405 write | Administrator audit list/detail reads succeeded, Student access was denied with HTTP 403, audit POST remained read-only with HTTP 405, and audit responses excluded unnecessary identity and credential information. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUD-02-audit-access-read-only-safe-response-tests-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-02A-student-cannot-access-audit-records-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06A-administrator-audit-records-list-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06B-administrator-audit-record-detail-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06C-audit-records-endpoint-read-only-pass.png |  | Not Required | Reused RBAC-06A/B/C for Administrator and read-only evidence. Added AUD-02A for explicit Student denial. | backend/administration/views.py; backend/administration/serializers.py; backend/administration/tests.py
S5-SEC-AUD-03 | Audit / Error Protection | Verify error and audit handling does not expose passwords, JWT tokens, API keys, credentials, stack traces, internal paths, or unsafe metadata. | System audit/error handling records safe categories and metadata only, without intentionally exposing protected secret or internal diagnostic information. | AUTOMATED + STATIC | ResumeGenerationAPITests.test_external_service_failure_creates_safe_system_audit_record; InterviewQuestionAPITests.test_semantic_validation_failure_logs_safe_category; InterviewFeedbackAPITests.test_feedback_validation_failure_logs_safe_category | N/A | N/A | N/A | N/A | Pass | Pass | N/A (automated/static) | Safe system audit metadata and validation logging were verified. Audit metadata rejects sensitive key names, external-service failure records retain only controlled operational fields, and interview validation logs use safe categories. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-AUD-03-safe-audit-and-error-handling-tests-pass.png |  | Not Required | Mapped safe audit/error tests passed 3/3. Static review confirmed sensitive metadata key blocking and safe log categorisation. | backend/administration/audit.py; backend/gradnavi/exceptions.py; backend/documents/tests.py; backend/interviews/tests.py
S5-SEC-SECRET-01 | Secret Protection | Verify repository tracking does not include real .env files, database passwords, AI API keys, JWT secrets, or other real credentials. | Repository review finds no committed real secrets. If a suspected secret is found, its value is not printed into retained evidence. | REPOSITORY REVIEW | No single automated test proves repository-wide secret absence | N/A | Repository-wide | N/A | N/A | N/A | Pass | N/A (repository review) | Backend tracked-file review found no committed real .env/private-key/credential files. backend/.env is ignored. Secret-name hits were references/placeholders only, and the real token-pattern scan returned no matches. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-01A-backend-secret-name-and-ignore-review-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-01B-backend-token-pattern-scan-pass.png |  | Not Required | Repository review completed without printing or retaining secret values. | .gitignore; backend/.env.example; repository tracked files
S5-SEC-SECRET-02 | Secret Protection | Verify AI provider credentials and backend secrets do not appear in frontend source or browser-facing configuration. | Frontend source and browser-facing configuration contain no backend secret values, AI API keys, database credentials, Django secrets, or administration credentials. | REPOSITORY REVIEW | No single automated test proves frontend-wide secret absence | N/A | frontend/ | N/A | N/A | N/A | Pass | N/A (repository review) | Frontend .env and .env.local are ignored. No tracked sensitive filename was found. Secret-name scan found token storage identifiers only, while real token-pattern scanning returned no OpenAI, GitHub, AWS, Slack, or JWT values. | Pass | Jerald | 2026-10-06 | docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-02A-frontend-secret-name-and-ignore-review-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-02B-frontend-token-pattern-scan-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-02C-frontend-tracked-sensitive-filename-scan-pass.png |  | Not Required | Frontend repository review completed without printing or retaining secret values. | frontend/src; frontend configuration; backend/gradnavi/settings.py
S5-SEC-FE-01 | Frontend Permission | Verify Administrator frontend routes reject unauthenticated and Student access while allowing the approved Administrator role. | After WBS 7.7 integration, unauthenticated and Student users cannot enter Administrator frontend routes. Administrator role receives approved access. | BROWSER / INTEGRATION | Backend role permission tests exist, but integrated Administrator frontend route is not present yet | Browser | Administrator frontend route after WBS 7.7 | Unauthenticated / Student / Administrator | Route-level access result | N/A | Pass | N/A (browser route) | Unauthenticated access to /admin and /admin/users redirected to /login. Authenticated Student access to the Administrator routes redirected to /profile. Authenticated Administrator access to /admin and /admin/users succeeded and loaded the approved Administrator interface. | Pass | Jerald | 2026-10-09 | EVD-057 manual browser verification, no screenshot retained |  | Not Required | WBS 7.7 dependency resolved after Administrator frontend integration. Manual browser permission verification completed on the current Sprint 5 baseline. No screenshot retained. | frontend/src/App.jsx; frontend/src/components/auth/ProtectedRoute.jsx; frontend/src/components/auth/AdminRoute.jsx; WBS 7.7 / PR #64
S5-SEC-DEP-01 | Deployment Security | Verify deployed Django configuration uses appropriate Debug, Allowed Hosts, CORS, environment-secret, HTTPS, and production error settings. | Production configuration disables unsafe development behaviour, restricts hosts/origins, uses environment-managed secrets, and returns controlled production errors. | DEPLOYMENT REVIEW | Deferred to deployment and production verification | Deployment review | Production backend configuration | N/A | N/A | N/A | Pass |  | Post-deployment security check reported PASS by project lead. Detailed configuration evidence has not been independently reviewed. | Pass | Jerald |  | docs/testing/evidence/sprint-5/deployment-security/README.md (DEP-01A to DEP-01D) |  | Not Required | Additional evidence captured 14 October 2026: Railway variable names reviewed; HTTPS authentication returned 401 with a controlled JSON error; approved CORS origin accepted; unapproved origin rejected. Full production configuration values not independently verified. Screenshots DEP-01A to DEP-01D uploaded to GitHub. | backend/gradnavi/settings.py; docs/system-design/security-architecture.md
S5-SEC-DEP-02 | Deployment Security | Verify deployed frontend and backend expose no protected secrets and use approved production communication paths. | Deployed browser assets and responses expose no protected secret values and frontend/backend communication uses the approved production path. | DEPLOYMENT REVIEW | Deferred to deployment and production verification | Deployment review | Production frontend and backend | N/A | N/A | N/A | Pass |  | Post-deployment security check reported PASS by project lead. Detailed configuration evidence has not been independently reviewed. | Pass | Jerald |  | docs/testing/evidence/sprint-5/deployment-security/README.md (DEP-02A to DEP-02B) |  | Not Required | Additional evidence captured 14 October 2026: Vercel production API URL confirmed as Railway HTTPS endpoint; authenticated production API request returned 200. Comprehensive browser asset secret-exposure review not independently verified. Screenshots DEP-02A and DEP-02B uploaded to GitHub. | frontend build; backend deployment configuration; docs/system-design/security-architecture.md

## Evidence Register
Evidence ID | Test Case ID | Evidence Type | Required | Evidence Status | Evidence Location | Result / Observation | Sensitive Data Check | Collected By | Collection Date | Notes
EVD-001 | S5-SEC-AUTH-01 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | LoginAPITests.test_successful_login_returns_tokens_and_safe_user_information; LoginAPITests.test_successful_login_issues_valid_jwt_tokens
EVD-002 | S5-SEC-AUTH-02 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | LoginAPITests.test_wrong_password_is_rejected_with_safe_error; LoginAPITests.test_nonexistent_email_is_rejected_with_same_safe_error; LoginAPITests.test_wrong_password_and_nonexistent_email_return_same_error
EVD-003 | S5-SEC-AUTH-03 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | CurrentUserAPITests.test_missing_authorization_header_is_rejected; CurrentUserAPITests.test_malformed_token_is_rejected; CurrentUserAPITests.test_refresh_token_cannot_authenticate_current_user_endpoint
EVD-004 | S5-SEC-AUTH-04 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | TokenRefreshAPITests.test_valid_refresh_token_succeeds_and_returns_rotated_tokens; TokenRefreshAPITests.test_original_refresh_token_cannot_be_reused_after_rotation; TokenRefreshAPITests.test_new_rotated_refresh_token_can_be_used_for_another_refresh
EVD-005 | S5-SEC-AUTH-05 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | LogoutAPITests.test_successful_logout_blacklists_submitted_refresh_token; LogoutAPITests.test_existing_access_token_remains_usable_until_expiry_after_logout
EVD-006 | S5-SEC-AUTH-06 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | PasswordResetAPITests.test_unknown_email_request_returns_same_safe_response_and_sends_no_email; PasswordResetAPITests.test_reset_request_response_does_not_expose_uid_or_token; PasswordChangeAPITests.test_valid_password_change_succeeds; PasswordChangeAPITests.test_incorrect_current_password_is_rejected; PasswordChangeAPITests.test_weak_new_password_is_rejected
EVD-007 | S5-SEC-RBAC-01 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdministrationPermissionTests.test_unauthenticated_users_cannot_access_admin_endpoints; AdministrationPermissionTests.test_non_admins_cannot_access_admin_detail_endpoints
EVD-008 | S5-SEC-RBAC-02 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdministrationPermissionTests.test_students_cannot_access_admin_endpoints; AdministrationPermissionTests.test_non_admins_cannot_access_admin_detail_endpoints
EVD-009 | S5-SEC-RBAC-03 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdministrationPermissionTests.test_student_cannot_create_career; AdminUserRoleStatusAuditTests.test_student_cannot_change_role_or_status; AdminLearningResourceReportReviewTests.test_student_cannot_access_report_detail_or_update
EVD-010 | S5-SEC-RBAC-04 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdminUserManagementTests.test_admin_cannot_change_role_or_active_status
EVD-011 | S5-SEC-RBAC-05 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdminUserRoleStatusAuditTests.test_admin_can_change_user_role_through_dedicated_endpoint; AdminUserRoleStatusAuditTests.test_admin_can_change_user_active_status_through_dedicated_endpoint; AdminUserRoleStatusAuditTests.test_invalid_role_change_is_rejected
EVD-012 | S5-SEC-RBAC-06 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdminAuditRecordTests.test_admin_can_list_and_retrieve_audit_records; AdminAuditRecordTests.test_audit_records_endpoint_is_read_only; AdminAuditRecordTests.test_audit_response_does_not_expose_user_email; AdminAnalyticsTests.test_analytics_response_exposes_no_student_data
EVD-013 | S5-SEC-OWN-01 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | StudentProfileReadAPITests.test_get_uses_authenticated_user_and_does_not_leak_cross_user_data
EVD-014 | S5-SEC-OWN-02 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | StudentProfilePatchAPITests.test_client_supplied_ownership_identifiers_are_rejected; StudentProfilePatchAPITests.test_cross_user_nested_id_is_rejected_without_modifying_other_profile; StudentProfilePatchAPITests.test_authenticated_user_cannot_patch_another_profile_with_query_parameters
EVD-015 | S5-SEC-OWN-03 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | RecommendationAPITests.test_authenticated_user_profile_is_used_exclusively; LearningRoadmapAPITests.test_student_profile_is_derived_from_request_user
EVD-016 | S5-SEC-OWN-04 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | JobDescriptionMatchAPITests.test_authenticated_profile_ownership
EVD-017 | S5-SEC-OWN-05 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | ResumeGenerationAPITests.test_authenticated_user_profile_is_used_exclusively; CoverLetterGenerationAPITests.test_authenticated_user_profile_is_used_exclusively; CoverLetterGenerationAPITests.test_client_cannot_select_another_student_profile; CoverLetterGenerationAPITests.test_student_profile_id_is_rejected
EVD-018 | S5-SEC-OWN-06 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | InterviewHistoryAPITests.test_post_creates_owned_session_metadata; InterviewHistoryAPITests.test_get_returns_only_authenticated_user_history; InterviewHistoryAPITests.test_user_id_is_rejected
EVD-019 | S5-SEC-IN-01 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | RegistrationAPITests.test_public_registration_cannot_create_privileged_user; AccountSettingsAPITests.test_email_and_role_are_read_only; CoverLetterGenerationAPITests.test_user_id_is_rejected; CoverLetterGenerationAPITests.test_profile_prompt_and_system_prompt_fields_are_rejected; InterviewRequestSerializerTests.test_question_request_rejects_user_id; InterviewRequestSerializerTests.test_question_request_rejects_client_prompt
EVD-020 | S5-SEC-IN-02 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdminUserRoleStatusAuditTests.test_invalid_role_change_is_rejected; AccountSettingsAPITests.test_gif_profile_photo_is_rejected; AccountSettingsAPITests.test_profile_photo_over_five_mb_is_rejected; StudentProfilePatchAPITests.test_invalid_proficiency_and_missing_reference_are_rejected; JobDescriptionMatchAPITests.test_unknown_fields_rejected
EVD-021 | S5-SEC-AI-01 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | ResumeGenerationServiceTests.test_approved_profile_context_reaches_provider_through_privacy_mapper; CoverLetterGenerationServiceTests.test_approved_profile_context_reaches_provider_through_privacy_mapper
EVD-022 | S5-SEC-AI-02 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | ResumeGenerationServiceTests.test_private_profile_fields_are_not_exposed_to_provider_prompt; CoverLetterGenerationServiceTests.test_private_profile_fields_are_not_exposed_to_provider_prompt
EVD-023 | S5-SEC-AI-03 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | ResumeGenerationAPITests.test_shared_ai_service_failure_returns_503; ResumeGenerationAPITests.test_response_validation_failure_is_sanitized_503; CoverLetterGenerationAPITests.test_provider_unavailable_returns_503; InterviewQuestionAPITests.test_provider_timeout_returns_503; InterviewQuestionAPITests.test_semantic_validation_failure_returns_controlled_502; InterviewFeedbackAPITests.test_provider_timeout_returns_503
EVD-024 | S5-SEC-AI-04 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | CoverLetterGenerationServiceTests.test_job_description_instructions_do_not_become_trusted_instructions; InterviewQuestionServiceTests.test_question_context_preserves_trust_boundary; InterviewFeedbackServiceTests.test_feedback_context_is_untrusted; JobDescriptionMatchAPITests.test_job_matching_output_is_independent_of_text_ai_provider
EVD-025 | S5-SEC-AUD-01 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdminAuditRecordTests.test_career_create_update_and_delete_create_audit_records; AdminAuditRecordTests.test_learning_resource_report_status_change_creates_audit_record
EVD-026 | S5-SEC-AUD-02 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | AdminAuditRecordTests.test_admin_can_list_and_retrieve_audit_records; AdminAuditRecordTests.test_audit_records_endpoint_is_read_only; AdminAuditRecordTests.test_audit_response_does_not_expose_user_email
EVD-027 | S5-SEC-AUD-03 | Automated Regression | Yes | Pass | docs/testing/evidence/sprint-5/security/automated-security-regression.txt | Mapped automated security coverage passed within the 330-test WBS 8.3 regression run. | No real secrets intentionally retained | Jerald |  | ResumeGenerationAPITests.test_external_service_failure_creates_safe_system_audit_record; InterviewQuestionAPITests.test_semantic_validation_failure_logs_safe_category; InterviewFeedbackAPITests.test_feedback_validation_failure_logs_safe_category
EVD-028 | S5-SEC-AUTH-01 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-01-valid-student-login-pass.png | Valid Student login returned HTTP 200 with access and refresh JWTs and safe user fields only. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | Postman validation passed 6/6.
EVD-029 | S5-SEC-AUTH-02 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-02A-wrong-password-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-02B-unknown-email-rejected-pass.png | Wrong password and unknown email both returned the same safe HTTP 401 invalid-credentials response without account information leakage. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | Wrong-password and unknown-email Postman checks passed.
EVD-030 | S5-SEC-AUTH-03 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-03A-missing-authorization-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-03B-malformed-access-token-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-03C-refresh-token-rejected-as-access-pass.png | Missing authorization, malformed access token, and refresh-token-as-access attempts were rejected with safe HTTP 401 responses. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | All protected-endpoint authentication rejection checks passed.
EVD-031 | S5-SEC-AUTH-04 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-04A-refresh-token-rotation-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-04B-original-refresh-token-reuse-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-04C-rotated-refresh-token-works-pass.png | Refresh rotation succeeded, the original refresh token was rejected after rotation, and the rotated refresh token remained usable. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | JWT refresh-token rotation contract verified.
EVD-032 | S5-SEC-AUTH-05 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-05A-student-logout-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-05B-logged-out-refresh-token-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-05C-existing-access-token-remains-valid-pass.png | Logout succeeded, the submitted refresh token was blacklisted and rejected, and the already-issued access token remained valid until expiry. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | Logout and documented access-token expiry behaviour verified.
EVD-033 | S5-SEC-AUTH-06 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06A-password-reset-safe-response-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06B-unknown-email-reset-safe-response-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06C-incorrect-current-password-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06D-weak-new-password-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06E-valid-password-change-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUTH-06F-original-password-restored-pass.png | Password reset used safe non-enumerating responses. Incorrect current password and weak new password were rejected. Valid password change succeeded and the original Student password was restored. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | Original Student test password restored after valid-change verification.
EVD-034 | S5-SEC-RBAC-01 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-01A-unauthenticated-admin-users-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-01B-unauthenticated-admin-user-detail-rejected-pass.png | Unauthenticated requests to Administrator collection and user-detail endpoints were rejected with HTTP 401 and exposed no protected data. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | Unauthenticated Administrator endpoint protection verified.
EVD-035 | S5-SEC-RBAC-02 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-02A-student-admin-users-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-02B-student-admin-user-detail-rejected-pass.png | Authenticated Student requests to Administrator collection and detail endpoints were rejected with permission_denied and HTTP 403. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | Student-to-Administrator RBAC boundary verified.
EVD-036 | S5-SEC-RBAC-03 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03A-student-admin-career-create-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03B-student-admin-role-change-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03C-student-admin-status-change-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03D-student-admin-analytics-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03E-student-admin-audit-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03F1-student-admin-report-detail-access-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03F2-student-admin-report-update-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03G-student-admin-resource-update-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-03H-student-admin-resource-delete-rejected-pass.png | Student create, update, delete, role, status, report-review, analytics, and audit operations were rejected with HTTP 403. Temporary report and learning-resource records were removed after testing. | PASS - screenshots exclude passwords, JWT values, API keys, and other secret values | Jerald | 2026-10-06 | All planned RBAC-03 Student denial operations passed. Temporary test records were cleaned up.
EVD-037 | S5-SEC-RBAC-04 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-04-general-admin-user-edit-protects-role-status-pass.png | General Administrator user editing preserved role and active status while allowing safe editable fields. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | General user-edit endpoint preserved server-controlled role and active status. Postman checks passed 6/6.
EVD-038 | S5-SEC-RBAC-05 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05A-dedicated-admin-role-change-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05B-dedicated-admin-status-change-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05C-invalid-admin-role-change-rejected-pass.png | Dedicated role/status changes succeeded for valid Administrator actions and invalid role input was safely rejected. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Dedicated role/status endpoint contract verified. Invalid role validation passed 6/6.
EVD-039 | S5-SEC-RBAC-06 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06A-administrator-audit-records-list-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06B-administrator-audit-record-detail-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06C-audit-records-endpoint-read-only-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06D-administrator-analytics-response-safe-pass.png | Administrator audit and analytics reads succeeded, audit writes were rejected, and responses avoided unnecessary sensitive values. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Audit read-only behaviour and analytics response minimisation verified.
EVD-040 | S5-SEC-OWN-01 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-01-student-profile-ignores-cross-user-identifiers-pass.png | Student Profile GET remained bound to the authenticated Student and did not expose cross-user identity or goal data. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Authenticated-profile isolation passed 6/6.
EVD-041 | S5-SEC-OWN-02 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02A-client-supplied-user-id-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02B-cross-user-career-goal-id-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02C-cross-user-query-parameters-cannot-redirect-profile-update-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02-database-state-verification-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-02-temporary-users-cleanup-pass.png | Ownership spoofing through user ID, nested CareerGoal ID, and query parameters was rejected or ignored; database state remained isolated. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Ownership spoofing rejected and database state verified. Temporary ownership users were removed after testing.
EVD-042 | S5-SEC-OWN-03 | Static Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-targeted-automated-tests-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-static-recommendation-ownership-check.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-static-learning-roadmap-ownership-check.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-03-static-query-ownership-check.png | Targeted automated tests and static review confirmed guidance services derive profile ownership from request.user. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Targeted automated coverage and static request.user ownership review completed.
EVD-043 | S5-SEC-OWN-04 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-04A-job-match-uses-authenticated-student-profile-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-04B-job-match-rejects-client-supplied-profile-identity-pass.png | Job Match used the authenticated Student Profile and rejected client-supplied profile identity. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Job Match authenticated-profile ownership and selector rejection verified.
EVD-044 | S5-SEC-OWN-05 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-05A-resume-rejects-client-supplied-student-profile-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-05B-cover-letter-rejects-client-supplied-student-profile-pass.png | Resume and Cover Letter generation rejected client-supplied Student Profile selectors. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Protected Student Profile selector rejection verified for both document-generation endpoints.
EVD-045 | S5-SEC-OWN-06 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06A-student-a-creates-owned-interview-history-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06B-student-a-sees-own-interview-history-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06C-client-supplied-interview-history-user-id-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06D-student-b-cannot-see-student-a-interview-history-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-OWN-06-student-b-fixture-created.png | Interview History records bound to the authenticated Student; Student B could not receive Student A history. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Interview History ownership binding and cross-user isolation verified.
EVD-046 | S5-SEC-IN-01 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-IN-01A-public-registration-cannot-create-privileged-user-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01B-account-settings-protect-email-and-role-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01C-cover-letter-rejects-client-supplied-user-id-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01D-cover-letter-rejects-protected-prompt-controls-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01E-interview-questions-reject-client-supplied-user-id-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-01F-interview-questions-reject-client-supplied-prompt-pass.png | Protected role, ownership, profile identity, prompt, and system-prompt inputs were ignored or rejected according to endpoint contracts. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Server-controlled role, ownership, profile identity, and prompt boundaries verified.
EVD-047 | S5-SEC-IN-02 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-05C-invalid-admin-role-change-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02A-gif-profile-photo-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02B-oversized-profile-photo-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02C-invalid-skill-proficiency-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02D-missing-interest-reference-rejected-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-IN-02E-job-match-rejects-unknown-student-profile-field-pass.png | Invalid roles, file types/sizes, proficiency values, missing references, and unsupported Job Match fields returned controlled validation errors. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | RBAC-05C is reused as the mapped invalid-role evidence. All remaining IN-02 invalid-input checks passed.
EVD-048 | S5-SEC-AI-01 | Static Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AI-01-approved-profile-context-privacy-mapper-tests-pass.png | Mapped AI privacy tests passed and static review confirmed only the approved five Student Profile sections enter AI context. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Mapped provider-context tests passed 2/2. Static review of backend/ai_services/safety/privacy.py confirmed the five-section allowlist.
EVD-049 | S5-SEC-AI-02 | Static Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AI-02-private-profile-fields-not-exposed-to-provider-prompt-pass.png | Mapped provider-prompt tests passed and static review confirmed private identity, credential, interest, personality, URL, timestamp, and internal-ID data stay outside AI context. | PASS - screenshots and static evidence exclude passwords, JWT values, API keys, database credentials, and other secret values | Jerald | 2026-10-06 | Mapped private-field provider-prompt tests passed 2/2. Static exclusion rules reviewed.
EVD-050 | S5-SEC-AI-03 | Static Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AI-03-controlled-ai-provider-failure-tests-pass.png | Six mapped AI provider/validation failure tests passed. Static review confirmed controlled 502/503 responses and sanitised logging/error behaviour. | PASS - no provider secret, stack trace, prompt, credential, API-key, token, or Student-content leakage observed | Jerald | 2026-10-06 | Mapped provider-failure tests passed 6/6 and static error-handling review passed.
EVD-051 | S5-SEC-AI-04 | Static Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AI-04-untrusted-content-and-deterministic-scoring-tests-pass.png | Trust-boundary tests confirmed user-supplied content stays untrusted and Job Match scoring remains deterministic without the text AI provider. | PASS - no secret values intentionally retained | Jerald | 2026-10-06 | Mapped trust-boundary and deterministic-scoring tests passed 4/4.
EVD-052 | S5-SEC-AUD-01 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01A-administrator-creates-audited-career-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01B-career-creation-audit-record-exists-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01C-administrator-updates-audited-career-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01D-career-update-audit-record-exists-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01E-administrator-deletes-audited-career-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01F-career-deletion-audit-record-exists-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01G-administrator-resolves-learning-resource-report-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-01H-learning-resource-report-status-audit-record-exists-pass.png | Career create/update/delete and Learning Resource Report status change produced the expected Administrator audit records and metadata. | PASS - audit responses excluded passwords, tokens, API keys, and credentials | Jerald | 2026-10-06 | Automated audit mutation tests passed 2/2. Postman lifecycle evidence passed.
EVD-053 | S5-SEC-AUD-02 | Postman | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUD-02-audit-access-read-only-safe-response-tests-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-AUD-02A-student-cannot-access-audit-records-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06A-administrator-audit-records-list-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06B-administrator-audit-record-detail-succeeds-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-RBAC-06C-audit-records-endpoint-read-only-pass.png | Administrator audit reads succeeded, Student access was denied, audit mutation was rejected, and response fields remained controlled. | PASS - no user email, password, token, API-key, or audit-record leakage to Student | Jerald | 2026-10-06 | Automated tests passed 3/3. RBAC-06 evidence reused where identical; AUD-02A added for Student denial.
EVD-054 | S5-SEC-AUD-03 | Static Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-AUD-03-safe-audit-and-error-handling-tests-pass.png | Safe audit/error tests and static review confirmed sensitive metadata key blocking, controlled external-service audit fields, and safe validation categories. | PASS - no passwords, JWTs, API keys, credentials, internal content, or Student answers retained in audit/log evidence | Jerald | 2026-10-06 | Mapped safe audit/error tests passed 3/3.
EVD-055 | S5-SEC-SECRET-01 | Repository Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-01A-backend-secret-name-and-ignore-review-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-01B-backend-token-pattern-scan-pass.png | Backend repository review found no tracked real secret files or real token-pattern matches. backend/.env is ignored. | PASS - scan output intentionally showed names/pattern categories only, not secret values | Jerald | 2026-10-06 | Secret-name hits were expected references/placeholders in env example, settings, tests, and documentation.
EVD-056 | S5-SEC-SECRET-02 | Repository Review | Yes | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-02A-frontend-secret-name-and-ignore-review-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-02B-frontend-token-pattern-scan-pass.png; docs/testing/evidence/sprint-5/security/S5-SEC-SECRET-02C-frontend-tracked-sensitive-filename-scan-pass.png | Frontend repository review confirmed .env/.env.local are ignored, no sensitive filenames are tracked, and no real token-pattern matches were found. | PASS - ACCESS_TOKEN and REFRESH_TOKEN hits were identifier names in authStorage.js, not retained token values | Jerald | 2026-10-06 | No backend secret, API key, credential, or real JWT/token value found in tracked frontend source.
EVD-057 | S5-SEC-FE-01 | Browser / Integration | Yes | Pass | Manual browser verification recorded in S5-SEC-FE-01, no screenshot retained | Unauthenticated Administrator-route access redirected to /login. Authenticated Student access redirected to /profile. Authenticated Administrator access to /admin and /admin/users succeeded. | PASS - no passwords, tokens, API keys, database credentials, or secret values retained | Jerald | 2026-10-09 | WBS 7.7 dependency resolved. Tested unauthenticated, Student, and Administrator route outcomes on the current Sprint 5 baseline.
EVD-058 | S5-SEC-DEP-01 | Deployment Review | Yes | Reported Pass |  | Project lead confirmed PASS following deployment. Independent configuration evidence not supplied. | Do not retain passwords, tokens, API keys, database credentials, or secret values |  |  | Reported 13 October 2026. Original evidence state: Deferred. Evidence location and actual execution details pending.
EVD-059 | S5-SEC-DEP-02 | Deployment Review | Yes | Reported Pass |  | Project lead confirmed PASS following deployment. Independent configuration evidence not supplied. | Do not retain passwords, tokens, API keys, database credentials, or secret values |  |  | Reported 13 October 2026. Original evidence state: Deferred. Evidence location and actual execution details pending.
EVD-060 | WBS-8.3-CLEANUP | Cleanup Verification | No | Pass | docs/testing/evidence/sprint-5/security/S5-SEC-CLEANUP-01-temporary-test-data-cleanup-verified-pass.png | Temporary audit Administrator, temporary report Student, related Student Profile, Learning Resource, Learning Resource Report, and temporary Administrator audit records were removed after evidence collection. | PASS - cleanup output contains identifiers/counts only and retains the real test.student@gradnavi.local account | Jerald | 2026-10-06 | Verification: temporary Administrator 0, temporary report Student 0, temporary resource 0, temporary report 0, real test Student 1.

## Defects
Defect ID | Test Case ID | Severity | Priority | Summary | Expected Result | Actual Result | Owner | Status | Fix Branch / Commit | Retest Result | Evidence | Notes