## UAT 12 Cases
Test Case ID | User Role | Scenario / Objective | Test Steps | Expected Result | Environment | Evidence Method | Manual Review Evidence | Actual Result | Status | Tester | Execution Date | Evidence File | Issue ID | Retest Status | Notes / Verification Boundary | Source / Implementation
UAT-01 | Student | Open homepage | Navigate to production site; review menu and Get Started control | Landing page loads with navigation and Get Started | Production | Browser / visual | Pass | Homepage and navigation visible | Pass |  |  | docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-001-Landing-Page.png |  | Not Required | Pass reported. Page image supports visible state, not all link destinations. | S5-PROD-EV-001
UAT-02 | Student | Create account and log in | Open sign-up; enter new account details; submit; sign in; view dashboard | Account created; Student Dashboard displayed | Staging and Production (reported) | Browser / functional | Pass | Account workflow reported completed; sign-up guidance visible | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-02-signup-password-rules.jpg; docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-002-Login-Page.png; S5-PROD-EV-003-Student-Dashboard.png |  | Not Required | Sign-up screenshot only proves form/password guidance. Staging sign-up and login described in PR #92. Production account-creation persistence not independently reproduced. | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099
UAT-03 | Student | Build Student Profile | Save skills, career goal, interests, education, experience and project; refresh | All entered profile values save and appear after refresh | Staging and Production (reported) | Browser / persistence | Pass | Structured profile evidence visible; profile-save message exists in earlier UAT evidence | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-03-profile-structured-evidence.jpg; docs/testing/evidence/sprint-5/uat/S5-UAT-EV-001-Student-Profile-Saved.png |  | Not Required | Each individual data field and persistence after refresh are not separately witnessed by the screenshot. PR #92 reports saving skill, goal and education in staging. | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099
UAT-04 | Student | View Career Recommendations | Open ranked matches and read explanation, match and readiness values | Ranked careers display match percentage, readiness and AI explanation | Production | Browser / integration | Pass | Ranked career, scores and explanation shown after reference-data import | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-04-career-recommendations-production.jpg | REFDATA-02 | Pass after fix (reported) | Before-state evidence for missing O*NET import kept separately. Screenshot demonstrates working display, not independent execution of every backend calculation. | docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-005-Career-Recommendations.png
UAT-05 | Student | View Skill Gap Analysis | Open skill gap for current career; compare readiness and gaps; add evidence and review changes | Readiness score, gaps and AI summary visible; score updates with evidence | Production | Browser / integration | Pass | Readiness and gap categories visible on production screen | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-05-skill-gap-production.jpg | OBS-AI-01 | Not Required | Staging AI explanation of 5.54 versus rounded 6% was reported in PR #92. Screenshot alone does not prove dynamic recalculation after adding evidence. | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099
UAT-06 | Student | View Learning Resources | Navigate to gap-linked learning recommendations | Learning resources shown for prioritised skill gap | Production | Browser / visual | Pass | Resource recommendations visible in production evidence | Pass |  |  | docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-009-Learning-Resources.png |  | Not Required | Resource relevance and outbound link availability not individually validated by this page screenshot. | docs/testing/evidence/sprint-5/production-verification/
UAT-07 | Student | Practise interview questions | Generate role-specific questions; type answer; request feedback; complete session | Questions, AI feedback and completion summary displayed | Production (reported); historical local supporting image | Browser / AI workflow | Pass | Question and feedback shown; final completion state reported | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-07-interview-feedback-existing-sprint4.jpg; docs/testing/evidence/sprint-5/uat/S5-UAT-EV-007-Interview-AI-Feedback.png |  | Not Required | The extracted feedback image belongs to earlier Sprint 4 testing, not a new Sprint 5 production execution. Screenshot does not independently prove completion summary. | docs/testing/evidence/sprint-5/uat/
UAT-08 | Administrator | Log in as Administrator | Sign in with an authorised admin account; load dashboard | Dashboard appears with current operational counts | Production | Browser / role access | Pass | Live Admin Dashboard counts visible | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-08-admin-dashboard-production-redacted.jpg |  | Not Required | Screenshot demonstrates authenticated admin screen state. Private account email in recent activity has been redacted. | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099
UAT-09 | Administrator | Manage users | Open Users; inspect list; attempt own-account deactivation | Users list displays; administrator is prevented from self-deactivation | Production (reported) | Browser / permission | Pass | User Management list visible; protective action reported | Pass |  |  | docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-016-Admin-User-Management.png |  | Not Required | Self-deactivation prevention is an assertion reported in test notes, not independently confirmed by screenshot alone. | docs/testing/evidence/sprint-5/security-permission/
UAT-10 | Administrator | View management sections | Open Careers, Skills, Resources and Reports sections | Each management page displays relevant data | Staging and Production (reported) | Browser / functional | Pass | Admin pages and editable management forms visible | Pass |  |  | docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-017-Admin-Career-Management.png; S5-PROD-EV-018-Admin-Skill-Management.png; S5-PROD-EV-019-Admin-Learning-Resource-Management.png; S5-PROD-EV-020-Admin-Resource-Reports.png |  | Not Required | Screenshots prove view/forms states; not all create/edit operations were saved and retested here. | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099
UAT-11 | Administrator | Change test user role and verify audit | Update test-user role; review resulting Audit Records entry | Role change saved and recorded with action, target, admin and timestamp | Staging and Production (reported) | Browser / audit | Pass | Production Audit Records row shows role change; staging workflow separately reported | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-11-audit-role-change-production-redacted.jpg |  | Not Required | The admin email was redacted. The source image shows a completed audit record; staging end-to-end role change was reported in PR #92. Entire production mutation chain not independently witnessed. | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099
UAT-12 | Any | Use site on mobile viewport | Resize to mobile; open Student/Admin pages; use collapsed menu | Mobile menu collapses and content stacks correctly | Frontend regression / production (reported) | Browser / responsive | Pass | Job Matching viewport and responsive layout screenshot available | Pass |  |  | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-12-job-matching-mobile-existing.jpg |  | Pass after fix (reported) | Selected mobile viewport only. WBS 8.5 Admin Dashboard heading overlap fixed in PR #95. | https://github.com/JeraldBucud/GradNavi/pull/95

## Evidence Index
Linked Test | Image filename | Description | GitHub evidence path | What the image proves / does not prove
UAT-02 | S5-UAT12-02-signup-password-rules.jpg | Sign-up password rules and form | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-02-signup-password-rules.jpg | Historical browser screen; no successful sign-up proof
UAT-03 | S5-UAT12-03-profile-structured-evidence.jpg | Student Profile structured evidence | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-03-profile-structured-evidence.jpg | No independent proof all fields persisted
UAT-04 | S5-UAT12-04-career-recommendations-production.jpg | Ranked Career Recommendations | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-04-career-recommendations-production.jpg | Production working-state screen
UAT-05 | S5-UAT12-05-skill-gap-production.jpg | Skill Gap Analysis | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-05-skill-gap-production.jpg | Production score/gaps, not before-after mutation
UAT-07 | S5-UAT12-07-interview-feedback-existing-sprint4.jpg | Interview AI feedback | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-07-interview-feedback-existing-sprint4.jpg | Previously executed Sprint 4 check, reused
UAT-08 | S5-UAT12-08-admin-dashboard-production-redacted.jpg | Admin Dashboard counts | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-08-admin-dashboard-production-redacted.jpg | Account email masked
UAT-11 | S5-UAT12-11-audit-role-change-production-redacted.jpg | Audit role change record | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-11-audit-role-change-production-redacted.jpg | Account email masked
UAT-12 | S5-UAT12-12-job-matching-mobile-existing.jpg | Mobile Job Matching screen | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-12-job-matching-mobile-existing.jpg | Single viewport, reused
REFDATA-01 | S5-UAT12-ISSUE-01-career-search-missing-reference-data.jpg | Career search before data import | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-ISSUE-01-career-search-missing-reference-data.jpg | Before-fix screen; reported issue
REFDATA-02 | S5-UAT12-ISSUE-02-recommendations-missing-onet-import.jpg | Recommendations unavailable before O*NET import | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-ISSUE-02-recommendations-missing-onet-import.jpg | Before-fix screen; reported issue

## Issues and Retests
Issue ID | Affected case | Observation | Environment | Original impact | Reported disposition | Evidence before / after | Closeout limit
REFDATA-01 | UAT-03 | Career/skill search returned no results without reference data | Staging then Production (reported) | Profile completion impeded | Fixed after reference data import (reported) | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-ISSUE-01-career-search-missing-reference-data.jpg; docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-03-profile-structured-evidence.jpg | Missing import is reported, individual import logs not independently reviewed
REFDATA-02 | UAT-04 | Career Recommendations returned reference data not ready | Production (reported) | Core recommendation temporarily unavailable | Fixed after O*NET demand snapshot import (reported) | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-ISSUE-02-recommendations-missing-onet-import.jpg; docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-04-career-recommendations-production.jpg | Later working state visible; import event not independently verified
UI-MOBILE-01 | UAT-12 | Admin mobile dashboard heading overlap | Responsive layout | Low visual impact | Fixed, PR #95 | docs/testing/evidence/sprint-5/uat/12-case/S5-UAT12-12-job-matching-mobile-existing.jpg; https://github.com/JeraldBucud/GradNavi/pull/95 | Admin mobile fix evidenced through PR and existing frontend regression; mobile image represents Job Matching
OBS-AI-01 | UAT-05 | Staging AI summary 5.54 vs displayed readiness 6% | Staging | Low narrative consistency | Reported to team, fix unconfirmed | https://github.com/JeraldBucud/GradNavi/pull/92#issuecomment-6107719099 | Do not claim production defect or resolved state without targeted verification
OBS-S5-001 | UAT-09 | User Management shows Last Login as Never | Staging and Production | Low informational impact | Open / future decision | docs/testing/evidence/sprint-5/production-verification/S5-PROD-EV-016-Admin-User-Management.png | Open limitation requiring owner disposition

## Case Crosswalk
12-case ID | Prior supporting record | Difference in definition
UAT-01 | Production S5-PROD-EV-001; old S5-UAT-09 | Homepage is explicit only in 12-case set
UAT-02 | Old S5-UAT-01; Production S5-PROD-EV-002 | Adds account creation
UAT-03 | Old S5-UAT-01 | Expanded profile field categories and refresh requirement
UAT-04 | Old S5-UAT-02 | Recommendation match with data-import fix
UAT-05 | Old S5-UAT-03 | Skill gaps and dynamic score
UAT-06 | Old S5-UAT-04 | Learning Resources, original also covered roadmap
UAT-07 | Old S5-UAT-08 | Interview Questions and feedback
UAT-08 | Old S5-UAT-11 | Admin Dashboard login and counts
UAT-09 | Old S5-UAT-10; WBS 8.3 | Adds self-deactivation protection
UAT-10 | Old S5-UAT-10 and S5-UAT-11 | Management lists and Reports
UAT-11 | Old S5-UAT-11; PR #92 | Adds role-change mutation plus audit
UAT-12 | Frontend WBS 8.2; PR #95 | Adds explicit mobile-responsive case

## Summary
GradNavi Sprint 5 UAT, 12-Scenario Register | Value
Total selected scenarios | 12
Reported Pass | 12
Reported Fail | 0
Reported Blocked | 0
Independently witnessed cases | Not established
Official previous register | 11-case record retained separately
Primary evidence | Saved screenshots and PR #92 staging comments
Approval | Pending formal group sign-off
Evidence selection | Screens show actual UI states; statements of execution are reported